Audit Status Report

As of March 17, 2009

State Legislative Audit Activities

Ongoing Activities

The Division of Legislative Audit completed field work on the Distance Education audit in July and conducted an exit conference with UA on July 31, 2008.   This review was focused primarily on the efficiency with which distance education courses are delivered and if technology has been utilized to the greatest extent possible.

We have not received the draft management letter as of current date.

External Audit Reports & Activities

Final Reports Issued:

UA Foundation and Consolidated Fund FY08 (KPMG) – No findings were reported.

Education Trust of Alaska FY08 (PWC) – No findings were reported.

UA FY08 A-133 Single Audit (KPMG) - One finding regarding student financial assistance.  A total of 19 title IV recipients from UAF, UAA, and UAS had withdrawn from courses but were not identified as withdrawn in a timely manner and funds were not correctly calculated for refund back to the awarding agency.  Or, as in one case, the refund was allocated to the wrong loan fund.  This finding was classified as a significant deficiency but not a material weakness.

KUAC FY08 Financial Statement and CPB Report (RJ&G) – No findings were reported but there was an adjusted misstatement pertaining to the write-off of potentially impaired equipment.  The amount was $34,500 and considered to be immaterial.  Therefore it was not corrected and will depreciate out through its natural life.

Work in Progress:

University of Alaska TRS, PERS, and SSA (SOA Department of Administration)

FY07 Incurred Costs for Fringe Benefits (DCAA)

FY08 Incurred Costs for Fringe Benefits (DCAA)

FY2009 Annual Audit Plan (Italic Items - have been completed or are in progress)

KPMG External Audit Support

Year-end cutoff

Inventory observation

Cash disbursements & bank transfers

Cash depositories

Auxiliary fund analysis

Unexpended Plant fund addition

Function and System Reviews

General Controls – in progress, this is an ongoing project

Continuous Controls Monitoring – in progress, this is an ongoing project

UAA

Cash Receipts

Departmental Review

Follow-up Audits

UAF

Cash Receipts

ProCard

Travel

Rural Campus Review:  CRCD Center for Distance Education and Rural College Bookstore

Follow-up Audits

UAS

Cash Receipts

Travel

Grants & Contracts Follow-up Audit

Information Systems Reviews

Data Security External Review Follow-up

Campus IT General Controls

Rural Campus Information Security

Statewide

Cash Receipts

Travel

Follow-up Audits

Special Requests

UAA Facilities Planning & Construction

OIT Risk Assessment – Banner Student Module – this is related to the Data Security External Review Follow-up under information systems reviews above

FY2009 Audit Plan Progress

Due to staff turnover, a newly implemented, mandatory rule at Statewide that we must wait two months minimum to begin recruitment for vacated positions, and time spent training new staff we are currently behind schedule with our annual audit plan that was approved in June 2008.  The audits that will not likely occur this year and the reason for each is explained in the chart below:

| Audit | Reason for Non-completion in FY09 |
| --- | --- |
| UAA Departmental Review | Auditor departure from the department on 12/1 plus the mandatory waiting period before recruiting to fill vacant positions |
| UAF Cash Receipts | One audit required three auditors, reducing into our time available for this audit |
| UAF ProCard | One audit required three auditors, reducing into our time available for this audit |
| SW Follow-up Audits | No fall 2008 student intern |
| Campus IT General Controls | Director aided new auditors with their assigned projects and could not complete planned IT audits |
| Rural Campus Information Security | Director aided new auditors with their assigned projects and could not complete planned IT audits |

Recruitment

A student intern began work on March 2 and will be with us for the spring semester at a minimum.  If she does not stay through the summer we will recruit for a summer intern.  We began recruitment for the vacant auditor position and are conducting interviews the week of March 16.

Other Department Activities

In January 2009 we began performing our Quality Assessment Review (QAR) per guidelines by the Institute of Internal Auditors.  The QAR is a separate agenda item for today’s meeting.