## Financial Systems
[5 empty] | Financial System or Automation-type Projects |  |  | Recently completed | [6 empty] | Estd Project Size: | Sm -est'd to take less than 3 months
[5 empty] | As of: November 2019 |  |  | In Progress | [7 empty] | Med - est'd to take between 3-8 months
[8 empty] | Not Started - Awaiting FinSys and/or OIT Resources | [7 empty] | Lrg - est'd to take over 8 months
[8 empty] | Not Scheduled - Awaiting Functional User Specs &/or campus agreement | [7 empty] | XLrg - est'd to take over 8 months & impacts large volume of employees
Does the Project Involve: | [7 empty] | Onbase/Record Retention Projects |  | Estd Project Size | [7 empty] | SW Fin/Sys or OIT Staff Assigned |  |  | Est'd volume OIT resourse needed | Outside Consulting Needed?
Revise Bus Proc | Add/Mod Banner Functionality | Add/Mod Other Systems | Add/Modify Reporting |  | Date Completed | Finance Category | Project Name | Purpose/Status/Comments | Initiator |  | Source of Request | Date Added |  | Classification | Status | Target Date | Project lead |  | Date Added to the list | RFP Process Needed?
Completed:
[5 empty] | 10/14 | General Finance | Banner Workflow upgrade | Features are beneficial for TEM and HR | Ellucian |  |  |  |  | Necessary upgrade | Completed
|  |  |  | External to Banner | 10/14 | Travel | Added TEM tables to RPTP | Allows users to do ad hoc queries/reporting and TEM/travel data | UA community |  |  |  |  | Enhances reporting capability | Completed
[5 empty] | 12/14 | General Finance | Banner Finance 8.10 upgrade | A required upgrade to stay on current version | Ellucian |  |  |  |  | System Requirement | Completed
|  |  |  | External to Banner | 12/14 | Accts Rec - Student | Touchnet 6.5 Upgrade | Added features and improved user interface | Touchnet |  |  |  |  | Necessary upgrade | Completed
|  |  |  | External to Banner | 1/15 | Non-Finance | MyHousing (UAA only) | Allows acceptance of credit card payments via Touchnet | [5 empty] | Implementation request | Completed
[5 empty] | 2/15 | Accts Rec - Student | Accounts Receivable 8.5 upgrade | A required upgrade to stay on current version | Ellucian |  |  |  |  | Necessary upgrade | Completed
|  |  |  | External to Banner | 2/15 | Accts Payable | Updated signature block for checks | Updated due to new Board of Regent Treasurer | Board of Regents |  |  |  |  | Requirement | Completed
|  |  |  | Mod | 3/15 | Property | Fixed assets modifications | Allows for better tracking of fixed asset transactions | Financial Systems |  |  |  |  | Necessary update | Completed
|  |  |  | Mod | 3/15 | Travel | Two new TEM reports in Production | FGR2TAR and FGRTER | TEM community | [5 empty] | Completed
[5 empty] | 4/15 | Travel | TEM upgrade to 8.7.0.4 | A required upgrade to stay current; adds enhanced functionality | TEM community |  |  |  |  | Neces | Completed
|  |  |  | External to Banner | 4/15 | General Finance | Vista Plus report updates | Allows for correct reporting of UA ID on Vista Plus | Financial Systems |  |  |  |  | Necessary update | Completed
|  |  |  | Mod | 4/15 | Property | Vehicle inventory enhancements | To streamline the collection from campuses of annual vehicle inventory required by State of AK | Controller |  |  |  |  | Improvement Request | Completed
[5 empty] | 5/15 | Accts Rec - Student | Single sign on for Touchnet | Streamlines the technical interface between UA Online and Touchnet | EAS |  |  |  |  | Improvement Request | Completed
[5 empty] | 06/15 | Accts Rec - Student | Accounts Receivable paper fixes | Benefits the Bursar's office for better identification of memo balance | Ellucian |  |  |  |  | Necessary update | Completed
[5 empty] | 07/15 | Accts Rec - Student | Single sign on for TMS | Streamlines the technical interface between UA Online and TMS | EAS | [5 empty] | Completed
|  |  |  | Mod | 07/15 | Accts Rec - Student | Display credit card refund policy on checkout | Per Visa Merchant Card agreement - must be compliant | Visa | [5 empty] | Completed
|  |  |  | Mod | 07/15 | Travel | Travel Module (TEM) & Onbase Integration | Provided capability to attach supporting travel documentation during the TEM process | TEM community | [5 empty] | Completed
[5 empty] | 07/15 | General Finance | Oracle 11.02.04 upgrade | Required upgrade to Oracle database | Tech Services | [5 empty] | Completed
|  |  |  | Mod | 08/15 | General Finance | FGR2FAR Report Fix | Aids capital project reporting; in testing now | SW Fund Acctg. |  |  |  |  | Necessary Fix | Completed
[5 empty] | 08/15 | Accts Rec - Student | Detail Code Review & Training from Ellucian | Contracted Ellucian to review detail code setup, review errors, provide training to team | AR Workteam | [5 empty] | Completed
|  |  |  | External to Banner | 09/15 | Property | Property Reporting for Financial Statements | Revised year end property processes for efficiency & created new reporting process for Fin Stmts | Financial Systems | [5 empty] | Completed
|  |  |  | Bus Proc | 09/15 | Accts Rec - Student | Touchnet security access transition to AR Dirs | Created & provided training to AR Dirs/Delegates and distributed Touchnet security/setup access | AR Workteam | [5 empty] | Completed
|  |  |  | External to Banner | 09/15 | General Finance | Payroll GL acct reconciliation query development | improved efficiency and ability to reconcile payroll recons more timely - reducing maint time for FinSys and OIT and enabling Recon Dept to manage their new process. | Financial Systems | [5 empty] | Completed
|  |  |  | Mod | 10/15 | Procurement | Purchase Order and Requisitions | Add date and time stamps to PO and REQs-eleviate manually writing info on every document | UAF Procurement | [5 empty] | Completed
|  |  |  | Mod | 10/15 | Accts Rec - Student | AR Student Payment Online changes | Requests to modify various UAOnline Student Billing/Payment info | AR Workteam | [5 empty] | Completed
|  |  |  | External to Banner | 10/15 | General Finance | Form Fusion Upgrade (Evisions) | Upgrade necessary to maintain support; affects checks, PO, Reqs, Student & Grant Bills etc | Financial Systems | [5 empty] | Completed
|  |  |  | Mod | 10/15 | Accts Rec - Student | 1098T letter process | Created more efficient process for printing/mailing letters, created tracking process | Financial Systems | [5 empty] | Completed
|  |  |  | Bus Proc | 2015-11-15 | Procurement | Procard/Travel Card process changes | Streamlining card distribution processes -cards are delivered directly to campuses & var exp date | Financial Systems | Sm |  |  |  |  | Completed | 2016-01-01 | Ali Hayden (SW FinSys) | AH
|  |  |  | Bus Proc | 2015-12-15 | Property | Account code modifications | Realligned & redefined property acct codes to comply cap proc & improve process efficiency in maintaining & reconciling property data. | Financial Systems | Sm |  |  |  |  | Completed | 2015-12-01 | Ali Hayden (SW FinSys) | AH, VG
[5 empty] | 2015-12-15 | General Finance | Banner Finance, General, & Workflow Upgrades | Necessary to stay on current versions | [7 empty] | 2015-12-01 | Vickie Gilligan (SW FinSys) | VG, SS, CD, SC
|  |  |  | External to Banner | 2015-12-15 | General Finance | Form Fusion Part 2 (Evilp & Maps) | Upgrade applications used by form fusion | Financial Systems | Sm |  |  |  |  | Completed | 2015-12-01 | Sushma Sonwalkar (SW OIT) | SS, RM, SC
|  |  |  | External to Banner | 2016-01-16 | Accts Rec - Student | Tuition Management System (TMS) - UAA | New app for UAA to provide self-service tution mgmt | UAA | Med |  |  | Sys Setup & Program | Implementation Request | Completed | 2015-12-01 | Charlene Roberstson (UAA AR) | SS, CD
[5 empty] | 2016-01-16 | General Finance | Single Sign On for Banner and Workflow | Improves user interaction, may reduce login instances, more eff self-service password mgmt | UA-Wide |  |  |  | Program | Improvement Request | Completed | 2016-01-01 | James Gentry (SW OIT) | VG
[5 empty] | 2016-02-16 | Non-Finance FinAid | Multi-Entity Processing (MEP) | Utilizes new Banner technology to eliminate the triplication of Fin Aid Banner instances | Financial Aid | Sm |  |  |  | Improvement Request | Completed | 2016-02-16 | Arthur Hussey (Sushma-Finance) | SS, CD
[5 empty] | 2016-03-01 | General Finance | Banner Finance, General, & Workflow Upgrades | Necessary to stay on current versions | [7 empty] | 2015-12-01 | Vickie Gilligan (SW FinSys) | VG, SS, CD, SC
|  |  |  | Mod | 2016-04-01 | Accts Rec - Student | PFD Garnishment Process | Streamlined creation, printing, mailing process for NOD letters to students- sig reduced FTE | AR Workteam | Med |  |  |  |  | Completed | 2016-04-01 | Vickie Gilligan (SW FinSys) | VG, CD,
|  |  |  | External to Banner | 2016-04-16 | Accts Rec - Student | Student Bill Emails | Modified emails to include Vet information re GI Bill | AR Workteam | sm |  |  |  |  | Completed | 2016-04-01 | Christine Dupee (SW FinSys) | CD, SS
[5 empty] | 2016-04-16 | Accts Rec - Student | AR Student Payment Online changes | UAF requested modifications to their fall payment options for students in UAOnline | UAF Bursers | sm |  |  |  |  | Completed | 2016-04-01 | Sushma Sonwalkar (SW OIT) | SS
[5 empty] | 2016-05-16 | Accts Rec - Student | PFD Garnishment Reporting | Add TSB2TRK table to be available in RPTP for reporting per campuses request | AR Workteam | sm |  |  |  |  | Completed | 2016-05-01 | Sushma Sonwalkar (SW OIT) | SS, VG
|  |  |  | External to Banner | 2016-06-01 | Accts Rec - Student | PayPath Credit Card Fee Charging | New Ap to charge students fee for paying w cr card reduces UA's cr card fees | Finance Directors | Med |  |  |  |  | Completed | not yet determined |  |  | 2016-02-26
|  |  |  | Mod | 2016-06-01 | Accts Rec - Student | Report of students w and wout direct deposit | Need to be able to access which students have/don't have direct deposit without having access to banking info - to initiate direct deposit campaigns to students. Created new view in RPTP GXRDIRD_AP and modified TGRAGES program so campuses could retrieve data at will. | AR workteam | Sm |  |  |  |  | Completed | not yet determined | Vickie Gilligan (SW FinSys) | VG, SS | 2016-03-30
|  |  |  | External to Banner | 2016-06-01 | Accts Rec - Student | Lumens non-credit course application | Finance part - integration with Banner via Touchnet & Transfirst, create accting process | SW OIT | Med | Baschky emails |  | Chg BP, Sys Setup |  | Completed | 2016-03-01 | Linda Bashky (SW OIT) | CD
|  |  |  | Bus Proc | 2016-07-01 | Budget/Grants & Contracts | Fund14 -Establish new fund type for matching funds | Change the year end roll rules for matching funds; needs to take effect in a new fiscal year - FY17 | Budget/Finance Dirs | Med | Jason Memo |  | Chg BP | Improvement Request | Completed | 2016-07-01 | Myron Dosch (SW Controller)
|  |  |  | External to Banner | 2016-07-01 | Accts Rec - Student | Touchnet SponsorPoint | A UAA-only solution to accept payments from student sponsors | UAA | Med |  |  | Sys Setup | Implementation Request | Completed | Unk-need Touchnet assist | Charlene Roberstson (UAA AR) | CD
|  |  |  | Bus Proc | 2016-07-01 | Procurement | Procard/Travel Card process changes | Reviewing & researching card contract change options for increased rebates. Signed a new contract with JP morgan joining the higher ed consortium contract. Doubles UA's rebate rate. Should provide an additional approx. $300,000 in rebates per year. | Financial Systems | Sm |  |  |  |  | Completed | not yet determined | Ali Hayden (SW FinSys) | AH, VG | 2015-11-01
|  |  |  | Bus Proc | 2016-08-01 | General Finance | Banner Access | Role provisioning: review and remove unnecessary 2nd level approval requirements and rely on campus security coordinator to make decision instead of requiring FinSys approval. | Finance Community | Med | UAF-23 |  |  |  | Completed | not yet determined | Vickie Gilligan (SW FinSys) |  | 2016-01-01
|  |  |  | External to Banner | 2016-08-01 | Non-Finance Housing | MyHousing (UAS, UAF, Kenai) | Housing application and payment system; available for testing for UAF and UAS | UAF & UAS | Sm |  |  |  | Implementation Request | Completed | when univ complete testing | Matthew Mund (Rita-Finance) | SC, CD
|  |  |  | External to Banner | 2016-08-01 | Accts Rec - Student | Enrollment RX-UAF | Finance part - integration with Banner via Touchnet & Transfirst, create accting process | UAA Student Area | Med | Ewing emails |  | Sys Setup |  | Completed | 2016-02-01 | Cathy Ewing (UAA Student Srv) | CD | 2015-10-01
|  |  |  | External to Banner | 2016-10-01 | Accts Rec - Student | Enrollment RX-UAA | Finance part - integration with Banner via Touchnet & Transfirst, create accting process | UAA Student Area | Med | Ewing emails |  | Sys Setup |  | Completed | 2016-02-01 | Cathy Ewing (UAA Student Srv) | CD | 2015-10-01
[5 empty] | 2016-10-01 | General Finance | Banner Finance, General Upgrades | Necessary to stay on current versions | [6 empty] | Completed | 2015-12-01 | Vickie Gilligan (SW FinSys) | VG, SS, CD, SC
[5 empty] | 2016-11-01 | General Finance | Improve Bank Load processes for Recons | Automate the Bank Load processes for AP and PR checks to improve the recon timing & efficiency | Financial Systems | sm |  |  |  |  | Completed | 2016-11-01 | Vickie Gilligan (SW FinSys) | VG, SS | 2015-08-01
|  |  |  | Mod | 2016-12-01 | Accts Rec - Student | 1098T mod to email notification | Resolve FERPA issue w SID in Subject and correct the population receiving the emails | AR Workteam | sm |  |  |  |  | Completed | 2016-12-01 | Christine Dupee (SW FinSys) | CD, SS | 2016-04-16
[5 empty] | 2016-12-01 | Accts Rec - Student | AR 8.5.2 upgrade | Required upgrade for 1098T reporting compliance | Financial Systems | Sm |  |  |  |  | Completed | 2016-12-18 | Christine Dupee (SW FinSys) | CD, SS | 2016-11-01
[5 empty] | 2017-01-01 | Accts Payable | 1099 electronically feed to Onbase | Create a process so the 1099's can be electronically fed to Onbase instead of manually scanning | Records Mgmt | Sm |  |  |  |  | Completed | 2017-01-01 | Lisa Sporleder (SW OIT) | VG, CD | 2016-11-01
|  |  |  | External to Banner | 2017-02-01 | Accts Rec - Student | Enrollment RX-UAS | Finance part - integration with Banner via Touchnet & Transfirst, create accting process | UAA Student Area | Med | Ewing emails |  | Sys Setup |  | Completed | 2017-02-01 | Cathy Ewing (UAA Student Srv) | CD | 2015-10-01
[5 empty] | 2017-02-01 | General Finance | Workflow upgrade 8.4 & 8.5 |  | OIT-EAS | Sm |  |  |  |  | Completed | 2017-01-01 | Dana Plata (SW OIT) | SC | 2016-08-01
[5 empty] | 2017-02-17 | Budget | UAOnline Budget Query implementation | Banner comes with some UAOnline budget query functionality that UA has not implemented. FinSys provided demos on functionality. Budget team would like to implement. FinSys to create the process to grant the security accesses for the process and implement. | Financial Systems | Sm |  |  |  |  | Completed | 2017-02-01 | Vickie Gilligan (SW FinSys) | VG | 2016-04-01
[5 empty] | 2017-03-01 | General Finance | Banner General & WebTailer Upgrades | Necessary to stay on current versions | OIT-EAS | Sm |  |  |  |  | Completed | 2015-12-01 | Jane Vohden (OIT) | SS | 2016-12-01
[5 empty] | 2017-03-01 | General Finance | Webspace Survey | Develop multiple complex Banner Finance data extracts for the Webspace Survey for the F&A rate development. | Tanya Hollis-SW Cost Analysis | Med |  |  |  |  | Completed | 2017-03-01 | Vickie Gilligan (SW FinSys) | VG | 2016-08-01
[5 empty] | 2017-03-01 | Budget | FBB2SBD table | add new fund field to FBB2SBD table to enhance budget offices reporting capabilities | Budget workteam | sm |  |  |  |  | Completed | 3/1/2017 | Vickie Gilligan (SW FinSys) | VG, SS | 2016-07-01
|  |  |  | Mod | 2017-04-17 | Accts Payable | Vendor ACH | Pay vendors electronically- modifying forms, exisiting reports and new email notification tested & completed. Users requested additional form mods - spec sent to OIT | Summit Team | Med | UAF-3 Julie |  | Sys Setup & Program | Efficiency improvement | Completed | 2017-04-01 | Vickie Gilligan (SW FinSys) | VG, AH, SS | Pre 2015
|  |  |  | Mod? | 2017-04-17 | Accts Payable & Procurement | Vendor ePymts w Single Use Acct (SUA) - Part 1 | Reviewing options/feasibility for epaymts to vendors using SUA (CR Card) which would increase UA's rebate and reduce cost of paper checks | Financial Systems | Med |  |  |  |  | Completed | 2017-05-01 | Ali Hayden (SW FinSys) | AH, VG | 2015-11-01
[5 empty] | 2017-05-17 | General Finance | Banner Finance, General Upgrades & paperfixes | Necessary to stay on current versions | [6 empty] | Completed | 2017-06-01 | Vickie Gilligan (SW FinSys) | VG, SS, CD, SC | 2017-05-01
[5 empty] | 2017-08-17 | Accts Rec - Student | Presidential Scholarship Detail Code Restructure | Implement new detail code structure for multitude of presidential scholarships to improve tracking, compliance, and efficiency | UA Scholars | sm |  |  |  |  | Completed | 2017-08-01 | Nicole Chambers(SW FinSys) | NC, VG | 2017-08-01
[5 empty] | 2017-08-17 | Accts Rec - Student | Adjunct Tuition Credit modifications | Implement Adjunct CBA changes for tuition credit program | Labor Relations | sm |  |  |  |  | Completed | 2017-08-01 | Nicole Chambers(SW FinSys) | NC, VG | 2017-06-01
[5 empty] | 2017-09-17 | General Finance | F&A Rate-CRIS Extract Mods | Modifications needed for the CRIS data extracts to be accurate and to work with the updated version of CRIS. | Tanya Hollis -SW Cost Analysis | TBD |  |  |  |  | Completed | 2017-09-01 | Vickie Gilligan (SW FinSys) | VG, NC | 2017-03-01
[5 empty] | 2017-10-01 | General Finance | Banner Finance, General Upgrades | Necessary to stay on current versions | [6 empty] | Completed | 2017-10-01 | Vickie Gilligan (SW FinSys) | VG, SS, NC | 2017-09-01
[5 empty] | 2017-12-01 | Budget | S report issues and mods | Budget workteam identified some problems needing corrected with the S report and some additional modifications to the report that they would like to improve their budget reporting. | Budget workteam | sm |  |  |  |  | Completed | 2017-12-01 | Vickie Gilligan (SW FinSys) | NC, VG, OIT staff | 2016-09-01
[5 empty] | 2018-02-01 | Procurement | Credit Card Compliance Monitoring | Research and implement JP Morgans compliance monitoring and reporting functionality to be used by Campus Card Administrators | CC workteam | sm |  |  |  |  | Completed | 2018-02-01 | Ali Hayden (SW FinSys) | AH | 2016-09-01
[5 empty] | 2018-03-01 | Accts Rec - Student | CTE 25% discount on select courses | Implement president's initiative to apply and track a 25% discount on select courses | Academic Affairs | sm |  |  |  |  | Completed | 2018-03-01 | Mike Earnest (UAF) | VG | 2018-03-01
[5 empty] | 2018-03-01 | Procurement | New Visa Card Program for Bulk Purchases | Implement a new Visa Card program to allow for bulk purchases from places like Costco, which don't accept mastercard. Instigated by the closing of Sam's Club | CC workteam | Sm |  |  |  |  | Completed | 2018-03-01 | Ali Hayden (SW FinSys) | AH | 2018-02-01
[5 empty] | 2018-04-01 | General Finance | Business Impact Analysis | Business Continuity study and process development | Risk Management | Sm |  |  |  |  | Completed | 2018-04-01 | Timothy Edwards (SW Risk) | VG | 2017-09-01
[5 empty] | 2018-05-18 | General Finance | Implement new FNBA Bank Website | Implement FNBA's new OnePay website and modify processes & security as needed | Cash Management | Sm |  |  |  |  | Completed | 2018-05-01 | Nicole Chambers(SW FinSys) | All FinSys Staff
[5 empty] | 2018-05-01 | General Finance | Oracle Reports desupport | Convert UA Finance reports from Oracle reports to Jasper or "C" and Implement reports before Oracle reports is desupported and the reports no longer work | OIT-EAS | Med |  |  |  |  | Completed | 2018-05-01 | Vickie Gilligan (SW FinSys) | VG, SS | 2016-10-01
[5 empty] | 2018-05-01 | General Finance | Report Modification FGR2FBL/FGR2FBF | Modify the report parameters to add additional parameter options | Fund Accounting | Sm |  |  |  |  | Completed | 2018-05-01 | Vickie Gilligan (SW FinSys) | SS | 2018-05-01
|  |  |  | External to Banner | 2018-06-01 | Accts Rec - Student | Tuition Management System (TMS) - UAS | New app for UAS to provide self-service tution mgmt. UAS will be added to the UAA contract for coverage. | UAS | Med |  |  | Sys Setup & Program | Implementation Request | Completed | not yet determined | Jodi VanKirk (UAS) | JL | 2017-09-01
[5 empty] | 2018-09-01 | General Finance | Banner TRNX to PREP conversion | Work toward eliminating the Banner TRNX environment to save support costs and convert Banner training to the PREP environment. Work through PREP dual purpose issues/processes and conversion of data issues. | OIT-EAS | Sm |  |  |  |  | Completed |  | Linda Baschky (SW OIT) | VG, SS | 2017-05-01
[5 empty] | 2018-10-01 | Procurement | Automate CR Card Application process | Implement JP Morgans online credit card application process to be used with UA's credit card program to eliminate paper and make the process more efficient and timely. Would like this implemented before the new travel card program is implemented. | Cr Card Team | Sm |  |  |  |  | Completed | 2018-08-01 | Ali Hayden (SW FinSys) | AH | 2018-06-01
|  |  |  | Bus Proc | 2018-11-01 | Procurement | Procard/Travel Card process changes | Project originally involved researching new card program functionality for one card and for limiting cards by MCC codes. However, due to impact of Travel Project, this project has now grown to include sunsetting the current travel cards, and implementing new UA Paid travel cards, a lodge card, and possible another option for infrequent travelers. | Financial Systems | Med |  |  |  |  | Completed | 2018-08-01 | Ali Hayden (SW FinSys) | AH, VG | 11/1/2015 - modified proj scope 1/2018
[5 empty] | 2019-01-01 | Accts Rec - Student | Contract Upload and Roll process | Implement a process to upload students to contracts and roll the contracts - save significant time each semester for the AR offices by reducing manual data entry | AR Workteam | Sm |  |  |  |  | Completed | 2019-01-01 | Cathy Ewing (SW FinSys) | CE, JP
|  |  |  | Bus Proc | 2019-01-01 | Accts Rec - Student | 1098T implement regulatory change | IRS has issued a regulatory change to require 1098T reporting on a Pymt basis instead of billed charge basis. This will require UA restructure DCAT/Detail Code setup to improve compliance reporting on 1098Ts, work with FinAid to determine scholarship impacts, and implementation of Ellucian Banner Changes as they are released. | AR Workteam | Lrg |  |  |  |  | Completed | 2019-01-01 | JP Landry (SW FinSys) | JL, VG | 2015-11-01
[5 empty] | 2019-06-01 | Accts Rec - Student | AR Mass Comment Upload | Implement process to mass upload comments to student accounts and stop having to data enter hundreds of comments manually on student accounts | AR Workteam | Sm |  |  |  |  | Completed | 2019-06-01 | Megan Colley (UAF), Cathy Ewing (SW) | CE
[5 empty] | 2019-07-01 | General Finance | Banner Upgrades | Necessary to stay on current versions & apply fixes | GFC | Sm |  |  |  |  | Completed | 2019-07-01 | GFC | All FinSys Staff
[5 empty] | 2019-07-01 | Procurement | Encumbrance cleanup project | Identify processes and liquidate and close old multi-year encumbrances to prevent them from continually rolling each FY and reduce FYE ecumbrance roll workload and encumbrance maintanance workloads. Research and implement new processes to keep the encumbrances clean on an ongoing basis. | Financial Systems | Med |  |  |  |  | Completed | 2019-07-01 | Cathy Ewing, Geoff Jacobs | GJ, CE
[5 empty] | 2019-07-01 | Budget | Org Hierarchy Restructure | Budget workteam revised the org hierarchy structure to improve reporting. All orgs had to be realigned to the new org hierarchy. | Budget workteam | Sm |  |  |  |  | Completed | 2019-07-01 | Harmonie Peters (SW) | CE
|  |  |  | Bus Proc | 2019-08-01 | Accts Rec - Student | Automate 3rd party payer payment application | Test changes to application of payment parameters recommended by Consultant | AR workteam | Sm |  |  |  |  | Completed | 2019-08-01 | Anastasia Brown (UAF AR) | JL | 2015-08-01
[5 empty] | 2019-09-01 | General Finance | AIM Upgrades | Supported Facilities Services on 2 AIM system upgrades and their interface with Banner. | Facilities Services | Sm |  |  |  |  | Completed | 2019-09-01 | Facilities (UAF) | CE
[5 empty] | 2019-10-01 | General Finance | Banner Upgrades | Necessary to stay on current versions & apply fixes | GFC | Med |  |  |  |  | Completed | 2019-10-01 | GFC | All FinSys Staff
|  |  |  | External to Banner | 2019-11-01 | Accts Rec - Student | ASAP non-credit course application | Finance part - integration with Banner via Touchnet & Transfirst, create accting process | UAA AR | Med |  |  |  |  | Completed | 2019-11-01 | Charlene Roberstson (UAA AR) (Charlene left in Jan 2018 - Kristin Elieff) | JL, VG | 2016-07-01
In Progress - Currently Using FinSys and/or OIT Resources
|  |  |  | Mod? |  | Accts Payable & Procurement | Vendor ePymts w Single Use Acct (SUA) - Part 2 & ACH Campaign | Work with procurement to develop a payment incentive plan that can be built into contracts and communicated to vendors to entice payment options of SUA and ACH over paper check processes. Create a Reconciliation interface between SUA payments and Banner. Have a second vendor recruitment campaign to increase vendor participation in SUA. | Financial Systems | Med |  |  |  |  | IP - Pilot for phone and web pymt SUA process in progress. ACH recruitment campaign began in August and continues. | not yet determined | Ali Hayden (SW FinSys) | AH, VG, HC | 2015-11-01
|  |  |  | Mod |  | Accts Payable/Travel | Travel Project Phase I (previously called Travel TEM replacement project - project scope has grown beyond TEM replacement) | Complete review and overhaul of the UA Travel Process including implementation of a TEM replacement application, a booking tool, a travel managment company, discount contracts, policy & reg revisions, etc. (Previous project description - Select and Imp new aps to replace TEM and possibly incorporate a travel booking tool) | Controller | XLrg |  |  |  |  | IP - All campuses are training and transitioning depts to Concur and the new process. All to be on Concur by 02/01/2020. | 02/01/2020 full implementation (excluding Student/Guest/Athletics) | Geoff Jacobs (Financial Systems) & Huron Consulting | GJ, VG, AH, SS | 2016-01-05
[5 empty] | added 09/2018 | Accts Rec - Student | Employee/Dep Tuition Waiver Process Imp | Creation of an employee and tuition waiver standard form and automated approval process using next gen forms. Adjust policy and contract functionality to improve efficiency of accepting and applying ETW's. | AR Workteam | Sm |  |  |  |  | The form is in PROD and being used by campuses. However, still awaiting policy change decision by BC or HRC to make the final improvements to the process. | 2020-04-01 | Cathy Ewing (SW FinSys) | CE
[6 empty] | Accts Rec - Student | DCAT & Detail Code Modifications | Modify the DCAT categories to be useful for student billing and reporting and apply consistently among all campuses. Correct Detail Code setup of thousands of detail codes so they are correct and we can start using various Banner functionality for application of payment, Title IV, Contracts, Auto refunds, etc. | AR Workteam | Lrg |  |  |  |  | IP - team has drafted the DCAT codes and in process of review detail code setups. | 2020-12-01 | Cathy Ewing (SW FinSys) | CE, VG, NC
|  |  |  | Bus Proc & mod? |  | Accts Rec - Student | Application of payment | Business Council approved project funding. Archive old records from system so we can implement application of payment. Prioritize the order for applying payments to charges, which will allow UA to use more of Banner's other automation features and help reduce administrative effort. This may impact the 1098T regulatory project. Hired an Ellucian Consultant October 2017 for 1 week and reviewed options for implementing application of payment at UA. Project is also dependant on the DCAT and Detail Code Mod Proj. | A/R Workteam | Lrg |  |  |  |  | IP- working with consultants to develop archiving process. | not yet determined | JP Landry (SW FinSys) | JP, NC, VG, SS | Pre 2015
|  |  |  | Mod | moved from "awaiting resources" to "In Progress" 04/2019 | Accts Rec - Student | Schedule Bill Format in uaonline | Business Council approved project funding. Schedule Bill format to be on uaonline for students - Creating a new UAOnline option for students to view a more consice bill and be able to select the bill by the term. Also allow registrars etc to see the bill as well. Business Council agreed to fund a portion of this project in Oct 2018. | AR workteam - Amanda Wall | Med | UAF-25 |  |  |  | IP-On Hold -Dependancies on Detail Code project and Application of payment projects. AR team has started assessing new online student billing format requirements. | not yet determined | UAF - Amanda Wall | VG, JL | User spec TR612 created and approved 05/2018
[6 empty] | Accts Rec - Student | Contract Upload Automation - Phase II | Business Council approved funding. Create a contract upload process to automate the payment/receipt handling for each of the participants in the contract. These are all manually keyed every semester. | AR workteam | Med |  |  |  |  | IP - Identifying other schools who have this process and working with them to determine options. | not yet determined | Cathy Ewing (SW FinSys) | CE
[6 empty] | Accts Rec - Student | Title IV Compliance & Process Improvement | Improve Title IV compliance and processing efficiencies by more fully utilizing the Banner system capabilities. | AR & FinAid Workteams | Med |  |  |  |  | IP- Team drafted new procedures. FinSys to develop some new reports. Team reviewing Banner functionality to realign processes. | not yet determined | Cathy Ewing (SW FinSys) | CE, VG
[6 empty] | Accts Rec - Student | Mass Fee Upload process | Business Coucil approved project funding. Investigate Banner delivered functionality for mass fee uploads and determine if will work for UA. Otherwise, develop a process. Similar to mass payment/receipt upload for contracts, this would significantly reduce manual keying effort and improve accuracy and efficiencies. | AR workteam | Med |  |  |  |  | IP - On hold - lower priority than other AR projects so being worked on as time permits. | not yet determined | Cathy Ewing (SW FinSys) | CE
[5 empty] | moved from "awaiting resources" to "In Progress" 06/2018 | Budget | Inter-Agency Receipts | Develop a process to better identify and remove inter-agency receipts from budget reporting | Budget Workteam | Med |  |  |  |  | IP - FinSys developed new RUCL. Campuses need to complete training and start using. FinSys needs to develop 1 report for SW Fund and SW Budget Depts. | not yet determined | Eric Johnson (SW Budget) | VG | 12/1/2017 Moved to In Progress 06/2018
[6 empty] | General Finance | Coversion to Banner 9 | Finance & AR will need to convert from Banner 8 to Banner 9 before the end of 2018. Finance and AR have 162 form mods that will be impacted by this implementation. | Financial Systems | Lrg |  |  |  |  | IP - B9 is up and running. A handful of finance forms need Ellucian fixes and are not reliable in B9. Awaiting 4 grant reports converted for B9. | 2018-10-01 | Nicole Chambers (SW FinSys) | VG, NC, JL,AH, GJ, EH, SS | 2016-09-01
[6 empty] | General Finance | Banner Oracle 12c and Tomcat server upgrades | Required upgrades to come into alignment with Ellucian Banner system requirements and to be able to apply regulatory upgrades | OIT | Med |  |  |  |  | IP - user testing of LRGP/BANQ enviroinment. Migration to PROD expected by end of Nov 2020. | 2019-12-01 | OIT | VG, NC, JL,AH, GJ, EH, SS
|  |  |  | Mod |  | General Finance | JV Automation in Banner | Allows electronic processing of JVs | UA Finance community | Lrg | UAF-1 Julie |  | Sys Setup & Program | New Request | IP - New JV Fupload & NextGen process is in pilot. | not yet determined | Cathy Ewing (SW FinSys), Briana Walters (UAF Budget) | CE, VG, SS, | 2015-08-01
[5 empty] | added 06/2019 | General Finance | Finance And Admin Redesign/Integration Project | In accordance with BOR direction, work to restructure Finance and Admin departments and functions to improve efficiencies and reduce cost. | President | Lrg |  |  |  |  | IP- On Hold awaiting Business Council direction | not yet determined | Myron Dosch, Vickie Gilligan (SW FinSys) | VG
|  |  |  | Mod | moved from 'not started" to IP 01/2019 | Grants & Contracts | Rehab proj-Sponsored award automation/reporting | Business Council approved a business assessment of the numerous compliance, automation and reporting needs requested by UAF OGCA. | Grant community | Med |  |  |  | Necessary & Efficiency | IP - Business Council funded initial businesss process assessment. Ellucian hired to perform assessment in Feb/March 2019. Ellucian assessment & work estimate completed and draft being reviewed by UA. | not yet determined | Rosemary Madnick (UAF OGCA) | VG, NC
|  |  |  | Bus Proc |  | Grants & Contracts | Old GAC conversion cleanup to close grants | Need to close old grants and improve grant reporting by researching & correcting errant records. Working on UAF grants first since more details available, then will continue with UAA & UAS grants. | UAF G&C | Lrg |  |  | Research |  | IP-project team mts wkly during academic year to determine fixes need on a per grant basis & then applies fixes - over 209 grants completed | Dec-2019 | Vickie Gilligan (SW FinSys) | VG, NC, SS | proj mtgs beg 3/22/2016
Not Started - Awaiting FinSys and/or OIT Resources
|  |  |  | Mod |  | Accts Payable | Stale dated to Unclaimed Property table | Provide functionality to electronically maintain (delete/upload) unclaimed property | Controller | Sm |  | 2015-03-01 | Program | Improvement Request | Await FinSys | not yet determined | Vickie Gilligan (SW FinSys)
|  |  |  | Mod | Still need? | Accts Payable/Travel | Direct Deposit process for travelers reimb-part 1 | Create report to identify employees w payroll auto dep but not a travel auto dep | UAF | Sm | UAF-2 Julie |  | Report |  | Await OIT | not yet determined
|  |  |  | Mod |  | Accts Payable/Travel | Direct Deposit process for travelers reimb-part 2 | Create automated process to populate travel dir dep info when updating Payroll dir dep info | UAF | Med | UAF-2 Julie |  | Chge BP & Program |  | Await PageUp Impl | not yet determined
|  |  |  | Mod | 07/2018 modified category and Project scope | Accts Payable/Travel | Sunsetting the TEM system after Concur Imp | After the Concur travel system is successfully implemented, UA will need to make decisions about sunsetting the TEM system, determining who should continue to have access and for how long, removing accesses that are no longer necessary, ensuring all documentation captured in Onbase, etc. (This project scope originally was only to automate the termination of employee access to the system.) | TEM Committee | Med |  |  |  |  | Await FinSys & OIT | not yet determined | Geoff Jacobs (SW FinSys) |  | Pre-2015 but modified scope 7/2018 from automating access termination to sunsetting the system.
|  |  |  | Mod |  | Accts Rec - Student | 1098-T Reprint functionality | Create Banner functionality so university personnel can reprint electronic 1098-T on demand |  | Sm |  |  |  |  | Await FinSys & Onbase | not yet determined
[6 empty] | Accts Rec - Student | Convert Student billing process to new process | Due to Ellucian student billing changes, UA is working on reviewing and implementing a new student billing process before the old process becomes obsolete and to get additional functionality that will make some processing more efficient for the business offices. | AR Workteam | Med |  |  |  |  | IP - On Hold - not a B9 issue as originally thought so the actually billing process is now a lower priority. | TBD | JP Landry (SW FinSys) | JL, SS
[6 empty] | Budget | UAOnline Budget Development Functionality | Banner comes with some UAOnline budget development functionality that UA has not implemented. Ellucian has provided an initial demo of the functionality. Team has requested FinSys create budget ID/Phase and roll in LRGP so team can better assess if will work for UA | Budget Workteam | Med |  |  |  |  | Demo provided - awaiting FinSys resources to setup LRGP | not yet determined | Vickie Gilligan (SW FinSys) | VG, SC | 2016-04-01
[5 empty] | added 03/2018 - | Budget | UAOnline B9 Finance Query Functionality | Deploy the new B9 UAOnline Finance Query Functionality | Budget Workteam | Sm |  |  |  |  | Functionality is available in LRGP. Awaiting BWT approval to move it to PROD | not yet determined | TBD | TBD | 2018-03-01
[6 empty] | General Finance | Ellucian Analytics | Implement Ellucian Analytics application | OIT | Med |  |  |  |  | IP- tool purchased, Imp team kickoff mtgs occuring | not yet determined | ? |  | 2018-01-01
|  |  |  | Mod |  | General Finance | Print to PDF capability from Evisions templates | Ability to print PO, REQ, Bills, (docs created by Evisions Templates) to PDF instead of Paper | UAF Procurement | Med | Julie emails | 2015-10-01 | Research |  | Await OIT | not yet determined |  |  | 2015-10-01
[6 empty] | General Finance | Depository Acct Reconciliation automation | Test and apply the existing Banner bank checking account reconciliation process to the depository account reconciliation process & determine if it would reduce time it takes campuses to reconcile depository accts. | UAF Finance-Bales | Sm |  |  |  |  | Await FinSys | not yet determined | Vickie Gilligan (SW FinSys) |  | 2016-04-01
[6 empty] | General Finance | Improve Student AR Reconciliation process | Need a more automated process to reconcile the AR subsidiary ledger to the GL and to help identify and resolve problems between the 2. | Controller | Med |  |  |  |  | Await FinSys | not yet determined |  |  | 2016-07-01
[6 empty] | General Finance | Qmenu/Qadhoc report conversion before desupported | Qmenu/Qadhoc reports with high usage need converted to another application, such as UAOnline Budget Queries, so they will be accessible when Qmenu/Qadhoc is desupported in June 2018 | Financial Systems | Sm |  |  |  |  | AwaitFinSys & OIT | before June 2018 |  |  | 2017-09-01
|  |  |  | External to Banner |  | General Finance | Project request & tracking process for Finance | Modify & update EAS Wiki for Fin projects & provide Directors ability to submit/monitor their requests | Financial Systems | Sm |  |  |  |  | IP - On Hold due to staffing shortage | not yet determined | Vickie Gilligan (SW FinSys) | VG | 2015-10-01
[6 empty] | General Finance | Security Employee Access Project | Define Security classes by EE Function and make it easier for Depts to submit security accesses at point of hire and also streamline security coordinator process | OIT - SWHR | Med |  |  |  |  | IP - On Hold by project leader Kelly McGee. Kelly has left. Project is stalled. | not yet determined | Linda Baschky (SW OIT) & Kelly McGee (SWHR) | VG, EH | 2017-11-01
|  |  |  | Bus Proc |  | Grants & Contracts | Grants w advanced payments- use acct 304? | Modify accounting process so grants that pay in advance don't distort grant receivables | UAF G&C | Sm | Rosemary Email |  | Chg BP |  | Await FinSys | not yet determined | Vickie Gilligan (SW FinSys) |  | 2016-03-01
|  |  |  | Mod |  | Procurement | PO & REQ Approval & Print Preview feature | A print preview feature for PO & REQ was requested. In disc's, was discovered would prefer a way to electronically route and approve. UA Online has the capability but requires setup & testine. This expands the project. | UAF | Med | UAF-8 |  |  |  | Await OIT | not yet determined
|  |  |  | Mod |  | Procurement | Vendor IDs | Stop the auto-populate function in the Vendor ID field; if the requisitioner leaves it blank; when printing a PO, the system auto-populates the space with the last ID that was entered – this causes undue work to verify every ID entered | UAF | Med | UAF-10 |  |  |  | Await OIT | not yet determined
|  |  |  | Mod |  | Property | Building Codes | Fix process that uploads building codes to scanners or wait for new scanners depending on timing | Property Coord |  |  |  |  | Necessary Fix | Await FinSys & OIT | not yet determined | Ali Hayden (SW FinSys) |  | 2016-03-01
|  |  |  | Bus Proc |  | Property | Building Codes & Equipment | Improve process associated with removal of buildings and associated equipment; Data cleanup | SW Budget | Med | Eric & Tanya Emails | 2015-09-01 |  |  | Await FinSys | not yet determined | Ali Hayden (SW FinSys) |  | 2016-03-01
[6 empty] | Property | New Inventory Scanners | Research, purchase, and implement new inventory scanners to replace the existing scanners. Most of the existing scanners do not work or not work well so the work is being done manually. | Property Coord | Lrg |  |  |  |  | Await FinSys | not yet determined | Ali Hayden (SW FinSys) |  | 2016-03-01
|  |  |  | Bus Proc |  | Property | Property Reconcilations | Streamlining recon process in preparation to distribute function to campuses -requires development of new queries/reports | Financial Systems | Med |  |  | Chg BP |  | IP - On Hold awaiting FinSys resources | not yet determined | Ali Hayden (SW FinSys) | AH, VG | Pre 2015
Not Started - awaiting functional user specifications &/or agreement of all campuses
|  |  |  | Mod |  | Accts Payable | Check printing - alpha character | Waiting on info from Cash Management | Cash Management |  |  |  |  | Improvement Request |  | not yet determined | Geri Rabbage
|  |  |  | Mod |  | Accts Payable | Vendor portal for ACH and other data | Establish a vendor portal so that vendors can update their own info (also see E-Procurement project) | Controller |  |  |  |  | Improvement Request |  | not yet determined | Myron Dosch (SW Controller)
[6 empty] | Accts Payable | OFAC compliance process modifications | Modify our OFAC monitoring processes for efficiency and compliance changes | Controller | [9 empty] | 2016-11-01
[6 empty] | Accts Rec - Misc | IRIS Conference Scheduling for UAA | UAA Implementation of IRIS application to be integrated with Touchnet. IRIS will be used for UAA to manage scheduling of conference rooms | UAA Conference Services | TBD |  |  |  |  | IRIS vendor working on system config.scheduled to be ready in Sept. Then we'll begin work on Touchnet integration. | not yet determined | Charlene Roberstson (UAA AR) & Pamela Mason (UAA) | CD, JP | 2017-03-01
|  |  |  | Bus Proc |  | Accts Rec - Student | Access for Schedule Bills | Creating a class for Schedule Bills so that staff can have access to print schedule bills rather than using TSAAREV in Banner | AR workteam |  | UAF-26
|  |  |  | Bus Proc & mod? |  | Accts Rec - Student | Auto-accept A/R charges | Streamline balancing of activity on student accounts | A/R Workteam | [6 empty] | not yet determined | Amanda Wall
|  |  |  | Mod |  | Accts Rec - Student | Automating student refunds | Automate student refund process; specifications need to be written. Coordinate among 3 universities | UAF PIT Project | [6 empty] | not yet determined | Amanda Wall
|  |  |  | Mod |  | Accts Rec - Student | Memo balance on student account | Better/complete info displayed on student accounts; may be corrected with upcoming Banner paper fix | A/R Workteam | [6 empty] | not yet determined | Charlene Robertson
|  |  |  | Mod |  | Accts Rec - Student | Refund notification | Automatic notifications to student during refund process |  |  | UAF-29 |  |  |  |  | not yet determined
|  |  |  | Mod |  | Accts Rec - Student | Text Messaging Student Reminders | Ability to send text notification messages as reminders to students; waiting on specifications | A/R Workteam |  |  |  |  | Improvement Request |  | not yet determined | Amanda Wall
|  |  |  | Mod |  | Accts Rec - Student | Student HOLD process modification | reconfiguration for the Banner form SOAHOLD, and other Banner components as necessary, to allow the tracking of hold edits and deletions by maintaining a history of changes to student holds, including the Banner user IDs for the changes. | Internal Audit | [6 empty] | not yet determined |  |  | 2016-03-23
[6 empty] | Budget | UAOnline Budget Transfer Functionality | Banner comes with some UAOnline budget transfer functionality that UA has not implemented. Budget team has received demo from Ellucian. Budget team to decide if/how to implement. | Budget Workteam | [6 empty] | not yet determined |  |  | 2016-04-01
|  |  |  | Mod |  | Budget | BAVL enhancement | An enhancement to "drill down" to detail from BAVL screen | Ellucian |  |  |  |  | Improvement Request |  | not yet determined
|  |  |  | Mod |  | Budget | BAVL -Incomplete Doc Changes | Modify Incomplete Doc Delete procedures to eliminate BAVL complications | UAF Budget |  | UAF-5 Julie |  |  |  |  | not yet determined
|  |  |  | Mod |  | Budget | Management reporting | Way to enter projections online; Someone would need to draft specifications - Need to research UAOnline Budget Projection functionality which may accommodate this process | Finance Community | Lrg | UAF-7 Julie |  |  | Improvement Request |  | not yet determined | need volunteer
[6 empty] | General Finance | AIM feed | Need to update and revamp the AIM feeds due to accounting issues | UAF FS | [6 empty] | not yet determined
|  |  |  | Mod |  | General Finance | Fund Accounting Report Enhancements | Fund Accounting needs to define report specifications | SW Fund Acctg. |  |  |  |  | New Request |  | not yet determined | Wei Guo
[6 empty] | General Finance | GASB Reporting | Improves year end financial statement preparation | Controller |  |  |  |  | Improvement Request |  | not yet determined | Wei Guo
|  |  |  | Mod |  | General Finance | Purging data out of Banner | More info is needed as to impact if purging is not done | [5 empty] | System Required |  | not yet determined | need volunteer
|  |  |  | External to Banner |  | General Finance | Reporting -data access improvements | either data warehouse or views in rptp | Finance Community | Lrg | UAF-6 Julie |  |  |  |  | not yet determined | need volunteer
|  |  |  | Bus Proc |  | General Finance | Reporting - Finance Data Training & Documentation | Enhance users understanding of Banner Finance tables to improve reporting | Statewide |  |  |  |  | Training |  | not yet determined | none
|  |  |  | External to Banner | still needed? | General Finance | Webspace automation for extracts - phase 2 | Convert the Access database designed in phase I to formal programs that OIT can support and Cost Accting can run. Moves work off Financial Systems ultimately and into Cost Analysis hands | Controller |  |  |  |  | Improvement Request |  | not yet determined | Tanya Hollis
|  |  |  | Mod |  | Grants & Contracts | InfoEd Implementation Project | Awaiting direction from project owner | UAF |  |  |  |  | Integration Request |  | not yet determined | unknown
|  |  |  | External to Banner |  | Non-Finance? | DRAW (Fusion Card System) | No formal request to Financial Systems has been made | UAF |  |  |  |  | Integration Request |  | not yet determined | unknown
[5 empty] | added 06/2018 | Procurement | Implement Receipt Imaging for Credit Card program | Implement JP Morgans receipt imaging functionality in PaymentNet to enhance users ability to track and reconcile their credit card transactions. | Cr Card Team | Sm | [5 empty] | not yet determined | Ali Hayden (SW FinSys) | AH | 2018-06-01
|  |  |  | External to Banner | Changed category from AP to Procurement 07/2018 | Procurement | Scan Credit Card receipts | Need solution to store procurement card receipts | ProCard Admins | Sm |  |  |  | New Request |  | not yet determined | need volunteer |  | Pre-2015
[6 empty] | Procurement | UAF Building Address Changes in Banner | UAF is in the process of changing all of their building addresses. This will affect the addresses the PO process uses in Banner when making purchases and where items/coorespondance will be sent. Automate the address change so it doesn't require manual entry. | UAF Procurement | Sm | [5 empty] | not yet determined | unknown |  | 2017-09-07
[6 empty] | Procurement | E-Procurement & Vendor Portal | Purchase and implement an e-procurement system that would automate more of the procurement process, have a vendor portal for interaction with vendors, and make the entire process more efficient. 3 e-procurement vendors are currently partnered with Ellucian Banner and may be good options. | Financial Systems | Lrg | [5 empty] | not yet determined |  |  | 2018-05-01
|  |  |  | Mod |  | Procurement | Bidder list automation | Need to determine status | Finance Community |  |  |  |  | Improvement Request |  | not yet determined | need volunteer
|  |  |  | Mod |  | Procurement | Improve W9 checking | Make email addresses and W9 information visible in PO screens FPAREQN & FPAPURR –P&CS and departments spends unnecessary time trying to discover if a W9 is already on file (or not) or if an entry into FTM2VND can be made | UAF |  | UAF-13
|  |  |  | Bus Proc | Combine scope with Travel Card/Procard process changes project in the IP project group? | Procurement | One-Card or Virtual Pay (V-Pay) procurement options | Combine/consolidate the university credit card options into a One Card or Virtual Pay transaction type for Procurement and Travel processing. Reduce limitations with respect to certain account codes (e.g. allowing charges for travel lodging on procurement cards) and provide greater flexibility for use and access to these tools. - Increasing use of a One-Card system designed with campus purchasing and traveler needs as the primary driver would reduce the need to reimburse employees for UA business activities & increase rebates. | UAF |  | UAF-12 |  |  |  |  | not yet determined | need volunteer
|  |  |  | Mod |  | Procurement | Procard Improved Information Tracking | When a procurement officer uses a ProCard; there is no way to track this in Banner – creating a field where this can be indicated would be helpful. - FIN SYS to think through REQ – CANCEL – PROCARD sequence. May be possible to comment “ProCard used”. | UAF |  | UAF-11 |  |  |  |  | not yet determined | need volunteer
|  |  |  | Mod |  | Procurement | Purchase order template change | Adds email address and url to UA contact blocks (changes FOM2CAD and PO Template) | UAF | [6 empty] | not yet determined
|  |  |  | Mod |  | Procurement | Remove duplicate NSF checking/over-riding at PO step | When no financial changes have been made from the REQ, currently overrides must be processed a second time during the procurement (first during REQ, then again during PO)- this is manual, adds no value, and causes delays. | UAF |  | UAF-14 |  |  |  |  | not yet determined
|  |  |  | External to Banner |  | Procurement | Reporting for Procurement | FIN SYS to develop a TOAD query to assist with identification of orphan lines; supply to UAF Procurement. | UAF |  | UAF-9 |  |  |  |  | not yet determined | need volunteer
|  |  |  | Mod |  | Procurement | Stop "touch every line" necessity | Occurs twice when processing POs | UAF |  | UAF-15
|  |  |  | Mod |  | Property | AiM Integration | Kit Duke and UAF have said a need will be forthcoming; no formal request has been made | UAF/Facilities |  |  |  |  | Integration Request |  | not yet determined | unknown
|  |  |  | Bus Proc |  | Property | Capital asset and depreciation on Banner | Automate depreciation calcuation, basis tracking, and related transaction postings | Controller |  |  |  |  | Improvement Request |  | not yet determined | Wei Guo
OnBase/Records and Retention Projects:
|  |  |  | External to Banner |  | Accts Rec - Student | Accounts Receivable | Identify all related documents UA wide; recommend retention; prep for OnBase and/or workflow | Finance Community | [6 empty] | not yet determined | need volunteer
|  |  |  | External to Banner |  | Accts Payable | Accounts Payable | Identify all related documents UA wide; recommend retention; prep for OnBase and/or workflow | Finance Community | [6 empty] | not yet determined | need volunteer
|  |  |  | External to Banner |  | Grants & Contracts | Grants and Contracts | Identify all related documents UA wide; recommend retention; prep for OnBase and/or workflow | Finance Community | [6 empty] | not yet determined | need volunteer