## 2026
Fiscal Year | 25 | 26
UA Strategy, Planning and Budget Calendar (last updated 5-22-2026) All dates are subject to change as more/different guidance becomes available or specific dates will be provided when instructions are distributed
Date | Responsible Party | Year | Action/Event | Audience | Operating Budget | Capital Budget | Performance | Personal Services | Notes
May - June | Legislature | FY27 | Leg: Budget submitted to Governor for signature and veto review Gov: Operating and capital bills are signed | Governor | Yes | Yes
May - August | MAUs | FY28 | Initial MAU performance reports created, including written analysis, definitions, baseline data | UA & MAU Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
May 21st | President and senior leadership | FY27 | -Operating and Capital Budget Appropriation Acceptance & Distribution Plan Approval -Natural Resources Fund Budget Allocation Approval | BOR | OBD Process | CBD Process
May 21st | UA Leadership | FY28 | Budget Guidance Discussion | BOR | Yes | Yes
June | SO SPB | FY28 | Distribute instructions regarding: Operating Budget Requests Capital Budget Requests Long Range Capital Plan Updates DM/R&R Backlog | MAUs | OBD Process | CBD Process
June 17th | MAUs | FY27 | Initial budget entries due | SO SPB | Yes
June 22nd | SO SPB | FY27 | Initial position budget entries to HR | SO HR | Yes
June 22nd | SO SPB | FY27 | Initial budget entries to Finance | SO Finance | Yes
June 23th - June 26th | SO HR | FY27 | -No position data entry (NBAPOSN/NBAPBUD) after 5pm until notified by SO HR -HR Budgets Rolls to Zero through Budget activation | MAUs | Yes |  |  | Yes
June 30th | SO Finance | FY27 | Temporary unrestricted budgets reversed and permanent budgets loaded | MAUs | Yes
July 1st |  | All | Fiscal year begins | UA | Yes | Yes |  | Yes
July | SO SPB | FY28 | Compensation and fixed cost budget estimates developed | MAUs | Yes |  |  | Yes
July | DoF | FY27 | New Capital Appropriation Collocation Codes Created/Distributed | SO SPB |  | CAT Process
July | SO SPB | FY27 | New Collocation Codes set up in Banner | MAUs |  | CAT Process
As Needed | MAUs | All | Funds Attached to Collocation Codes | SO SPB |  | CAT Process
July 17th | MAUs | FY26 | Final Authorized: balance budget and expenditures in Banner (suballocation, ABS code, and fund source) prior to SO Finance roll | SO SPB | Yes
July 18th | SO Finance | FY26 | Fiscal year roll in Banner | UA | Yes
July 20th | SO Finance | FY26 | TVEP Year-end Balance entries | UA | Yes
July 27th | MAUs | FY27 | Management Plan: balanced operating budget in Banner (suballocation, ABS code, and fund source) | SO SPB | Yes
July (late) | SO SPB | FY28 | Issue instructions for MAU level budget narratives | MAUs | Yes
July 31st | SO SPB | FY27 | Management Plan Budget (including personal services report) in ABS | OMB | Yes |  |  | Yes
August 5th | MAUs | FY28 | Submit: Operating Budget Requests Capital Budget Requests Long Range Capital Plan DM/R&R Backlog | SO SPB | OBD Process | CBD Process
August (mid) | MAUs | FY27 | Deferred Maintenance Expenditure Projections Submitted | SO SPB |  | CAT Process
August (mid) | Chancellors | FY28 | Review and Provide input: Operating and Capital Budget Requests | President and senior leadership | OBD Process | CBD Process
August (end of month) | MAUs | FY28 | Initial performance analyses published by MAUs on OMB web site for public viewing, and used by UA Leadership in discussion during initial meetings with OMB. | OMB |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September - November | MAUs | FY28 | Final MAU performance reports entered, including written analysis, definitions, baseline data, in alignment with the overall budget. | UA Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports Note: Content changes made later in this period typically undergo review, and may require OMB approval to publish.
September (early) | SO SPB | FY27 | Deferred Maintenance Expenditure Report Submitted | OMB |  | CAT Process
September (early) | UA Leadership | FY28 | Initial Meetings with state agencies | Leg. Fin. & OMB | OBD Process | CBD Process
Sept - 2nd | UA Leadership | AY28 | Discussion and Approval of Tuition Rates | BOR | Yes
Sept - 3rd | SO SPB | FY28 | Review: Operating Budget Request Capital Budget Request Long Range Capital Plan DM/R&R Backlog | BOR | OBD Process | CBD Process
September (late) | SO SPB | FY26 | Final Authorized and Actual Scenarios due in ABS | OMB | Yes
September (late) | SO SPB | FY27 | Authorized Budget Distribution Document (Yellowbook) Published | UA
September (late) | MAUs | FY27 | Capital Appropriation Status Updates (CASR) | SO SPB |  | CAT Process
October (early) | SO SPB | FY27 | Capital Appropriations Status Reports (CASR) | OMB |  | CAT Process
October | MAUs | FY28 | Complete MAU Level Operating Budget Narratives & Org Charts | SO SPB | Yes
October (late) | SO SPB | FY28 | UA Level Narrative submitted in ABS | OMB | Yes
October (late) | SO SPB | FY28 | Submitted in ABS: Operating Budget Capital Budget | OMB | OBD Process | CBD Process
Nov - 5th | SO SPB | FY27 | Capital Committed Funds & Transfer Reports | BOR |  | CAT Process
Nov - 5th | UA Leadership | FY28 | Approval: Operating Budget Request Capital Budget Request Second Review: Long Range Capital Plan | BOR | OBD Process | CBD Process |  |  | No substantial changes (dollar amount, title or description) can be made after BOR approval.
Nov - 5th | SO Finance | FY26 | Financial Statements Audited Financial Statements Available | BOR
November | SO SPB | FY28 | Deferred Maintenance/Renewal & Repurposing Backlog submitted | OMB |  | CBD Process
November (mid) | SO SPB | FY28 | MAU Level Operating Budget Narratives & Org Charts in ABS | OMB | Yes
November (end of month) | MAUs | FY28 | Final MAU performance analysis published via OMB action on website for public viewing and locked until next cycle. | OMB |  |  | PME Process |  | Hard stop due date set by SO SPB, as select content is included in both UA Budget book and Governor's Budget Proposal. In recent years, this has occurred in early December.
December 15th | Governor | FY28 | Budget Proposal submitted to Legislature | Legislature | Yes | Yes
December (mid) | SO SPB | FY28 | Gov/UA Budget Book released | OMB | Yes | Yes | Yes | Yes | NOTE: Once this is submitted, OMB will not allow changes to published performance analysis content until the next reporting cycle.
December | SO SPB | FY28 | Discuss possible budget amendments | OMB | Yes | Yes
January (early) | SO SPB | FY27 | Submit supplemental request(s) | OMB | Yes | Yes
January (mid) | SO SPB | FY28 | Submit amendment request(s) | OMB | Yes | Yes
January | SO SPB | FY28 | Operating and Capital Budget Document Published (aka Redbook) | UA | OBD Process | CBD Process | Yes
January | Legislature | All | Legislative Session Begins 3rd Tuesday in January | State of Alaska | Yes | Yes
January (late) | MAUs | FY27 | Mid-year Financial Review | UA Leadership | Yes
February (mid) | Governor | FY28 | Amended budget released | Legislature | Yes | Yes
Feb - March | UA Leadership | FY27 | Supplemental Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY28 | Amendment Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY28 | Budget Request - Legislative Status Report | BOR | Yes | Yes
March - Apr | MAUs | FY27 | Lapsing Capital Appropriations Review/Extension Requests | SO SPB |  | CAT Process
April - 15th | UA Leadership | AY28 | Tuition Rate Notice (letter from the President per BOR P05.10.060) | BOR
April | UA Leadership | FY27 | Budget Request - Legislative Status Report | BOR | Yes | Yes
April (late) | MAUs | FY27 | University Spring Management Report Review | UA Leadership | Yes | Yes
April - June | SO SPB | FY27 | Lapsing Capital Appropriations Reviewed/Extended | DoF through OMB |  | CAT Process
April - June | SO SPB | FY28 | Operating and Capital Budget Distribution Plan Recommendation Developed | UA Leadership | OBD Process | CBD Process
May 26th | SO SPB | FY27 | Capital Committed Funds & Transfer Reports | BOR |  | CAT Process
May 26th | SO SPB | FY28 | Operating and Capital Budget Distribution Plan Approved | BOR | OBD Process | CBD Process
Note on A25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Get this date from the FYxx Budget Development Guidelines document Alesia/President drafts in May

## 2025
Fiscal Year | 24 | 25
UA Strategy, Planning and Budget Calendar (last updated 4-30-2025) All dates are subject to change as more/different guidance becomes available or specific dates will be provided when instructions are distributed
Date | Responsible Party | Year | Action/Event | Audience | Operating Budget | Capital Budget | Performance | Personal Services | Notes
May - August | MAUs | FY27 | Initial MAU performance reports created, including written analysis, definitions, baseline data | UA & MAU Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
May - June | President and senior leadership | FY26 | -Operating and Capital Budget Appropriation Acceptance -Operating and Capital Budget Distribution Plan Approval -Natural Resources Fund Budget Allocation Approval | BOR | OBD Process
June | SO SPB | FY27 | Distribute instructions regarding: Submitting Operating & Capital Budget Requests Updating the Long Range Capital Plan | MAUs | OBD Process | CBD Process
June | UA Leadership | FY27 | Budget, Goals, and Measures Planning Discussion | BOR | Yes |  | Yes
June - 17th | MAUs | FY26 | Initial budget entries due | SO SPB | Yes
June - 23rd | SO SPB | FY26 | Initial budget entries to Finance | SO Finance | Yes
June - 23rd | SO SPB | FY26 | Initial position budget entries to HR | SO HR | Yes
June 24th - June 27th | SO HR | FY26 | -No position data entry (NBAPOSN/NBAPBUD) after 5pm until notified by SO HR -HR Budgets Rolls to Zero through Budget activation | MAUs | Yes |  |  | Yes | Scroll to Fiscal Year Close Procedures
June - 30th | SO Finance | FY26 | Temporary unrestricted budgets reversed and permanent budgets loaded | MAUs | Yes |  |  |  | Scroll to Year End Instructions
July 1st |  | All | Fiscal year begins | UA | Yes |  | Yes | Yes
July | SO SPB | FY27 | Compensation and fixed cost budget estimates developed | MAUs | Yes |  |  | Yes
July | DoF | FY26 | New Capital Appropriation Collocation Codes Created/Distributed | SO SPB |  | CAT Process
July | SO SPB | FY26 | New Collocation Codes set up in Banner | MAUs |  | CAT Process
As Needed | MAUs | All | Funds Attached to Collocation Codes | SO SPB |  | CAT Process
July | SO SPB | FY27 | Instructions for completing ABS narrative sections issued | MAUs | Yes
July - 18th | MAUs | FY25 | Final Authorized: balance budget and Expenditures in Banner (allocation, object code, and fund source) prior to SO Finance roll | SO SPB | Yes
July - 19th | SO Finance | FY25 | Fiscal year roll in Banner | UA | Yes
July 21st | SO Finance | FY25 | TVEP Year-end Balance entries | UA | Yes
July - 23rd | MAUs | FY26 | Management Plan: balanced operating budget in Banner (allocation, object code, and fund source) | SO SPB | Yes
August 1st | SO SPB | FY26 | Management Plan Budget, (including personal services report) Scenario | OMB | Yes |  |  | Yes
August 4th | MAUs | FY27 | Submitted: Operating Budget Requests Capital Budget Requests Long Range Capital Plan DM/R&R Backlog | SO SPB | OBD Process | CBD Process
August | MAUs | FY26 | Deferred Maintenance Expenditure Projections Submitted | SO SPB |  | CAT Process
August | MAUs | FY27 | Universities Budget Meeting | UA Leadership | Yes
August | Chancellors | FY27 | Review and Provide input: Operating and Capital Budget Requests | President and senior leadership | OBD Process | CBD Process
August (end of month) | MAUs | FY27 | Initial performance analyses published by MAUs on OMB web site for public viewing, and used by UA Leadership in discussion during initial meetings with OMB. | OMB |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September - November | MAUs | FY27 | Final MAU performance reports entered, including written analysis, definitions, baseline data, in alignment with the overall budget. Note: Content changes made later in this period typically undergo review, and may require OMB approval to publish. | UA Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September (early) | SO SPB | FY27 | Deferred Maintenance/Renewal & Repurposing Backlog submitted | OMB |  | CBD Process
September | SO SPB | FY26 | Deferred Maintenance Expenditure Projections Submitted | OMB |  | CAT Process
September | UA Leadership | AY27 | Discussion and Approval of Tuition Rates | BOR | Yes
Aug/Sept | SO SPB | FY27 | Review: Operating Budget Request Capital Budget Request Long Range Capital Plan | BOR | OBD Process | CBD Process
September | SO SPB | FY25 | Final Authorized and Actual Scenarios due in ABS | OMB | Yes
September | UA Leadership | FY27 | Initial Meetings with Legislative Finance Division | Leg. Fin. | OBD Process
September | UA Leadership | FY27 | Initial Meetings with OMB | OMB | OBD Process
September | SO SPB | FY26 | Capital Appropriation History Updated | UA |  | CAT Process
September (late) | SO SPB | FY26 | Authorized Budget Distribution Document (Yellowbook) Published | UA
October | MAUs | FY27 | Complete MAU Level Operating Budget Narratives & Org Charts for ABS | SO SPB | Yes
October | SO SPB | All | Capital Committed Funds & Transfer Reports Created | BOR |  | CAT Process
October (late) | SO SPB | FY27 | UA Level Narrative Submitted | OMB | Yes
November (early) | UA Leadership | FY27 | Approval: Operating Budget Request Capital Budget Request Second Review: Long Range Capital Plan | BOR | OBD Process | CBD Process
November (early) | SO Finance | FY25 | Financial Statements Audited Financial Statements Available | BOR
November (early) | MAUs | FY26 | Due: Capital Appropriation Status Updates (CASR) | SO SPB |  | CAT Process
November | SO SPB | FY26 | Due: Capital Appropriations Status Reports (CASR) | OMB |  | CAT Process
November | SO SPB | FY27 | MAU Level Operating Budget Narratives & Org Charts in ABS | OMB | Yes
November | SO SPB | FY27 | Submitted: Operating Budget Capital Budget | OMB | OBD Process | CBD Process
November (end of month) | MAUs | FY27 | Final MAU performance analysis published via OMB action on website for public viewing and locked until next cycle. | OMB |  |  | PME Process |  | Hard stop due date set by SO SPB, as select content is included in both UA Budget book and Governor's Budget Proposal. In recent years, this has occurred in early December.
December | SO SPB | FY27 | Due: Gov/UA Budget Book NOTE: Once this is submitted, OMB will not allow changes to published performance analysis content until the next reporting cycle. | OMB | Yes | Yes | Yes | Yes
December 15th | Governor | FY27 | Budget Proposal submitted to Legislature | Legislature | Yes | Yes
January (early) | SO SPB | FY26 | Submit supplemental request(s) to OMB | OMB | Yes | Yes
January (early) | SO SPB | FY27 | Discuss possible budget amendments with OMB | OMB | Yes | Yes
January (late) | MAUs | FY26 | Mid-year Financial Review | UA Leadership | Yes
January | SO SPB | FY27 | Operating and Capital Budget Document Published (aka Redbook) | UA | OBD Process | CBD Process | Yes
January | Legislature | All | Legislative Session Begins 3rd Tuesday in January | State of Alaska | Yes
Feb - March | UA Leadership | FY26 | Supplemental Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY27 | Amendment Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY27 | Budget Request - Legislative Status Report | BOR | Yes | Yes
Feb - March | Governor | FY27 | Amended budget scenario released | Legislature | Yes | Yes
March - Apr | MAUs | FY26 | Lapsing Capital Appropriations Review/Extension Requests | SO SPB |  | CAT Process
April (late) | MAUs | FY26 | University Spring Management Report Review | UA Leadership | Yes | Yes
April - 15th | UA Leadership | AY27 | Tuition Rate Notice (letter from the President per BOR P05.10.060) | BOR
April | UA Leadership | FY26 | Budget Request - Legislative Status Report | BOR | Yes | Yes
April - June | SO SPB | FY26 | Lapsing Capital Appropriations Reviewed/Extended | DoF through OMB |  | CAT Process
April - May | SO SPB | FY27 | Operating and Capital Budget Distribution Plan Recommendation Developed | UA Leadership | OBD Process | CBD Process
April (late) | SO SPB | All | Capital Committed Funds & Transfer Reports Created | BOR |  | CAT Process
May - June | Legislature | FY27 | Leg: Budget submitted to Governor for signature and veto review Gov: Operating and capital bills are signed | Governor | Yes | Yes
May | SO DAIR | FY28 | Updated Draft Performance Management Evaluation Procedures Distributed | MAUs |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
May | SO Finance | FY27 | Temporary budgets rolled in Banner | MAUs | Yes |  |  |  | Link to Finance year end calendar

## 2024
Fiscal Year | 23 | 24
UA Strategy, Planning and Budget Calendar (last updated 5-31-2024) All dates are subject to change as more/different guidance becomes available or specific dates will be provided when instructions are distributed
Date | Responsible Party | Year | Action/Event | Audience | Operating Budget | Capital Budget | Performance | Personal Services | Notes
May - August | MAUs | FY26 | Initial MAU performance reports created, including written analysis, definitions, baseline data | UA & MAU Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
May/June | President and senior leadership | FY25 | -Operating and Capital Budget Appropriation Acceptance -Operating and Capital Budget Distribution Plan Approval -Natural Resources Fund Budget Allocation Approval | BOR | OBD Process
June | SO SPB | FY26 | Distribute instructions regarding: Submitting Operating & Capital Budget Requests Updating the Long Range Capital Plan | MAUs | OBD Process | CBD Process
June | UA Leadership | FY26 | Budget, Goals, and Measures Planning Discussion | BOR | Yes |  | Yes
June - 18th | MAUs | FY25 | Initial budget entries due | SO SPB | Yes
June - 24th | SO SPB | FY25 | Initial budget entries to Finance | SO Finance | Yes
June - 24th | SO SPB | FY25 | Initial position budget entries to HR | SO HR | Yes
June 24th - July 1st | SO HR | FY25 | -No position data entry (NBAPOSN/NBAPBUD) after 5pm until notified by SO HR -HR Budgets Rolls to Zero through Budget activation | MAUs | Yes |  |  | Yes | Scroll to Fiscal Year Close Procedures
June - 28th | SO Finance | FY25 | Temporary unrestricted budgets reversed and permanent budgets loaded | MAUs | Yes |  |  |  | Scroll to Year End Instructions
July 1st |  | All | Fiscal year begins | UA | Yes |  | Yes | Yes
July | SO SPB | FY26 | Compensation and fixed cost budget estimates developed | MAUs | Yes |  |  | Yes
July | DoF | FY25 | New Capital Appropriation Collocation Codes Created/Distributed | SO SPB |  | CAT Process
July | SO SPB | FY25 | New Collocation Codes set up in Banner | MAUs |  | CAT Process
As Needed | MAUs | All | Funds Attached to Collocation Codes | SO SPB |  | CAT Process
July | SO SPB | FY26 | Instructions for completing ABS narrative sections issued | MAUs | Yes
July - 19th | MAUs | FY24 | Final Authorized: balance budget and Expenditures in Banner (allocation, object code, and fund source) prior to SO Finance roll | SO SPB | Yes
July - 20th | SO Finance | FY24 | Fiscal year roll in Banner | UA | Yes
July - 24th | MAUs | FY25 | Management Plan: balanced operating budget in Banner (allocation, object code, and fund source) | SO SPB | Yes
August 1st | SO SPB | FY25 | Management Plan Budget, (including personal services report) Scenario | OMB | Yes |  |  | Yes
August 1st | MAUs | FY26 | Submitted: Operating Budget Requests Capital Budget Requests Long Range Capital Plan DM/R&R Backlog | SO SPB | OBD Process | CBD Process
August | MAUs | FY25 | Deferred Maintenance Expenditure Projections Submitted | SO SPB |  | CAT Process
August | SO SPB | FY26 | 10-yr Revenue Projections | OMB
August | MAUs | FY26 | Universities Budget Meeting | UA Leadership | Yes
August | Chancellors | FY26 | Review and Provide input: Operating and Capital Budget Requests | President and senior leadership | OBD Process | CBD Process
August (end of month) | MAUs | FY26 | Initial performance analyses published by MAUs on OMB web site for public viewing, and used by UA Leadership in discussion during initial meetings with OMB. | OMB |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September - November | MAUs | FY26 | Final MAU performance reports entered, including written analysis, definitions, baseline data, in alignment with the overall budget. Note: Content changes made later in this period typically undergo review, and may require OMB approval to publish. | UA Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September (early) | SO SPB | FY26 | Deferred Maintenance/Renewal & Repurposing Backlog submitted | OMB |  | CBD Process
September | SO SPB | FY25 | Deferred Maintenance Expenditure Projections Submitted | OMB |  | CAT Process
September | UA Leadership | AY26 | Discussion and Approval of Tuition Rates | BOR | Yes
Aug/Sept | SO SPB | FY26 | Review: Operating Budget Request Capital Budget Request Long Range Capital Plan | BOR | OBD Process | CBD Process
September | SO SPB | FY24 | Final Authorized and Actual Scenarios due in ABS | OMB | Yes
September | UA Leadership | FY26 | Initial Meetings with Legislative Finance Division | Leg. Fin. | OBD Process
September | UA Leadership | FY26 | Initial Meetings with OMB | OMB | OBD Process
September | SO SPB | FY25 | Capital Appropriation History Updated | UA |  | CAT Process
September (late) | SO SPB | FY25 | Authorized Budget Distribution Document (Yellowbook) Published | UA
October | MAUs | FY26 | Complete MAU Level Operating Budget Narratives & Org Charts for ABS | SO SPB | Yes
October (late) | SO SPB | FY26 | UA Level Narrative Submitted | OMB | Yes
November (early) | UA Leadership | FY26 | Approval: Operating Budget Request Capital Budget Request Second Review: Long Range Capital Plan | BOR | OBD Process | CBD Process
November (early) | SO Finance | FY24 | Financial Statements Audited Financial Statements Available | BOR
November | SO SPB | FY26 | MAU Level Operating Budget Narratives & Org Charts in ABS | OMB | Yes
November | SO SPB | FY26 | Submitted: Operating Budget Capital Budget | OMB | OBD Process | CBD Process
November (end of month) | MAUs | FY26 | Final MAU performance analysis published via OMB action on website for public viewing and locked until next cycle. | OMB |  |  | PME Process |  | Hard stop due date set by SO SPB, as select content is included in both UA Budget book and Governor's Budget Proposal. In recent years, this has occurred in early December.
December | SO SPB | FY26 | Due: Gov/UA Budget Book NOTE: Once this is submitted, OMB will not allow changes to published performance analysis content until the next reporting cycle. | OMB | Yes | Yes | Yes | Yes
December 15th | Governor | FY26 | Budget Proposal submitted to Legislature | Legislature | Yes | Yes
December (late) | MAUs | FY25 | Due: Capital Appropriation Status Updates (CASR) | SO SPB |  | CBD Process
January (early) | SO SPB | FY25 | Due: Capital Appropriations Status Reports (CASR) | OMB |  | CBD Process
January (early) | SO SPB | FY25 | Submit supplemental request(s) to OMB | OMB | Yes | Yes
January (early) | SO SPB | FY26 | Discuss possible budget amendments with OMB | OMB | Yes | Yes
January | SO SPB | FY26 | Operating and Capital Budget Document Published (aka Redbook) | UA | OBD Process | CBD Process | Yes
January | Legislature | All | Legislative Session Begins 3rd Tuesday in January | State of Alaska | Yes
Feb - March | UA Leadership | FY25 | Supplemental Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY26 | Amendment Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY26 | Budget Request - Legislative Status Report | BOR | Yes | Yes
Feb - March | Governor | FY26 | Amended budget scenario released | Legislature | Yes | Yes
March (early) | MAUs | FY25 | Lapsing Capital Appropriations Review/Extension Requests | SO SPB |  | CAT Process
April (early) | MAUs | FY25 | University Spring Management Report Review | UA Leadership | Yes | Yes
April - 15th | UA Leadership | AY26 | Tuition Rate Notice (letter from the President per BOR P05.10.060) | BOR
April | UA Leadership | FY25 | Budget Request - Legislative Status Report | BOR | Yes | Yes
April - June | SO SPB | FY25 | Lapsing Capital Appropriations Reviewed/Extended | DoF |  | CAT Process
April | SO SPB | FY26 | Operating and Capital Budget Distribution Plan Recommendation Developed | UA Leadership | OBD Process | CBD Process
April (late) | SO SPB | All | Capital Committed Funds & Transfer Reports Created | BOR |  | CAT Process
May | Legislature | FY26 | Leg: Budget submitted to Governor for signature and veto review Gov: Operating and capital bills are signed | Governor | Yes | Yes
May | SO DAIR | FY27 | Updated Draft Performance Management Evaluation Procedures Distributed | MAUs |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
May | SO Finance | FY26 | Temporary budgets rolled in Banner | MAUs | Yes |  |  |  | Link to Finance year end calendar

## 2023
Fiscal Year | 22 | 23
UA Strategy, Planning and Budget Calendar (last updated 5-22-2023) All dates are subject to change as more/different guidance becomes available or specific dates will be provided when instructions are distributed
Date | Responsible Party | Year | Action/Event | Audience | Operating Budget | Capital Budget | Performance | Personal Services | Notes
May - August | MAUs | FY25 | Initial MAU performance reports created, including written analysis, definitions, baseline data | UA & MAU Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
June | President and senior leadership | FY24 | -Operating and Capital Budget Appropriation Acceptance -Operating and Capital Budget Distribution Plan Approval -Natural Resources Fund Budget Allocation Approval | BOR | OBD Process
June | SO SPB | FY25 | -Distribute instructions regarding: -Submitting Operating & Capital Budget Requests -Updating the 6-yr Capital Improvement Plan | MAUs | OBD Process | CBD Process
June | UA Leadership | FY25 | Budget, Goals, and Measures Planning Discussion | BOR | Yes |  | Yes
June - 20th | MAUs | FY24 | Initial budget entries due | SO SPB | Yes
June - 26th | SO SPB | FY24 | Initial budget entries to Finance | SO Finance | Yes
June - 26th | SO SPB | FY24 | Initial position budget entries to HR | SO HR | Yes
June 26th - June 30th | SO HR | FY24 | -No position data entry (NBAPOSN/NBAPBUD) after 5pm until notified by SO HR -HR Budgets Rolls to Zero through Budget activation | MAUs | Yes |  |  | Yes | Scroll to Fiscal Year Close Procedures
June - 30th | SO Finance | FY24 | Temporary unrestricted budgets reversed and permanent budgets loaded | MAUs | Yes |  |  |  | Scroll to Year End Instructions
July 1st |  | All | Fiscal year begins | UA | Yes |  | Yes | Yes
July | SO SPB | FY25 | Compensation and fixed cost budget estimates developed | MAUs | Yes |  |  | Yes
July | DoF | FY24 | New Capital Appropriation Collocation Codes Created/Distributed | SO SPB |  | CAT Process
July | SO SPB | FY24 | New Collocation Codes set up in Banner | MAUs |  | CAT Process
As Needed | MAUs | All | Funds Attached to Collocation Codes | SO SPB |  | CAT Process
July | SO SPB | FY25 | Instructions for completing ABS narrative sections issued | MAUs | Yes
July - 14th | MAUs | FY23 | Final Authorized: balance budget and Expenditures in Banner (allocation, object code, and fund source) prior to SO Finance roll | SO SPB | Yes
July - 15th | SO Finance | FY23 | Fiscal year roll in Banner | UA | Yes
July - 24th | MAUs | FY24 | Management Plan: balanced operating budget in Banner (allocation, object code, and fund source) | SO SPB | Yes
July - 31st | SO SPB | FY24 | Management Plan Budget (including personal services report) Scenario Due | OMB | Yes |  |  | Yes
August 1st | MAUs | FY25 | Submitted: Operating Budget Requests Capital Budget Requests 6-yr Capital Improvement Plan DM/R&R Project list | SO SPB | OBD Process | CBD Process
August | MAUs | FY24 | Deferred Maintenance Expenditure Projections Submitted | SO SPB |  | CAT Process
August | SO SPB | FY25 | 10-yr Revenue Projections | OMB
August | MAUs | FY25 | Universities Budget Meeting | UA Leadership | Yes
August | Chancellors | FY25 | Review and Provide input: Operating and Capital Budget Requests | President and senior leadership | OBD Process | CBD Process
August (end of month) | MAUs | FY25 | Initial performance analyses published by MAUs on OMB web site for public viewing, and used by UA Leadership in discussion during initial meetings with OMB. | OMB |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September - November | MAUs | FY25 | Final MAU performance reports entered, including written analysis, definitions, baseline data, in alignment with the overall budget. Note: Content changes made later in this period typically undergo review, and may require OMB approval to publish. | UA Leadership |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September (early) | SO SPB | FY25 | Deferred Maintenance/Renewal & Repurposing Project list submitted | OMB |  | CBD Process
September | SO SPB | FY24 | Deferred Maintenance Expenditure Projections Submitted | OMB |  | CAT Process
September | UA Leadership | AY25 | Discussion and Approval of Tuition Rates | BOR | Yes
September | SO SPB | FY25 | Review: Operating Budget Request Capital Budget Request 6-yr Capital Improvement Plan | BOR | OBD Process | CBD Process
September | SO SPB | FY23 | Final Authorized and Actual Scenarios due in ABS | OMB | Yes
September | UA Leadership | FY25 | Initial Meetings with Legislative Finance Division | Leg. Fin. | OBD Process
September | UA Leadership | FY25 | Initial Meetings with OMB | OMB | OBD Process
September | SO SPB | FY24 | Capital Appropriation History Updated | UA |  | CAT Process
September (late) | SO SPB | FY24 | Authorized Budget Distribution Document (Yellowbook) Published | UA
October | MAUs | FY25 | Complete MAU Level Operating Budget Narratives & Org Charts for ABS | SO SPB | Yes
October | SO SPB | All | Capital Committed Funds & Transfer Reports Created | BOR |  | CAT Process
October (late) | SO SPB | FY25 | UA Level Narrative Submitted | OMB | Yes
November (early) | UA Leadership | FY25 | Approval: Operating Budget Request Capital Budget Request 6-yr Capital Improvement Plan | BOR | OBD Process | CBD Process
November (early) | SO Finance | FY23 | Financial Statements Audited Financial Statements Available | BOR
November | SO SPB | FY25 | MAU Level Operating Budget Narratives & Org Charts in ABS | OMB | Yes
November | SO SPB | FY25 | Submitted: Operating Budget Capital Budget | OMB | OBD Process | CBD Process
November (end of month) | MAUs | FY25 | Final MAU performance analysis published via OMB action on website for public viewing and locked until next cycle. | OMB |  |  | PME Process |  | Hard stop due date set by SO SPB, as select content is included in both UA Budget book and Governor's Budget Proposal. In recent years, this has occurred in early December.
December | SO SPB | FY25 | Due: Gov/UA Budget Book due NOTE: Once this is submitted, OMB will not allow changes to published performance analysis content until the next reporting cycle. | OMB | Yes | Yes | Yes | Yes
December 15th | Governor | FY25 | Budget Proposal submitted to Legislature | Legislature | Yes | Yes
December (late) | MAUs | FY24 | Due: Capital Appropriation Status Updates (CASR) | SO SPB |  | CBD Process
January (early) | SO SPB | FY24 | Due: Capital Appropriations Status Reports (CASR) | OMB |  | CBD Process
January (early) | SO SPB | FY24 | Submit supplemental request(s) to OMB | OMB | Yes | Yes
January (early) | SO SPB | FY25 | Discuss possible budget amendments with OMB | OMB | Yes | Yes
January | SO SPB | FY25 | Operating and Capital Budget Document Published (aka Redbook) | UA | OBD Process | CBD Process | Yes
January | Legislature | All | Legislative Session Begins 3rd Tuesday in January | State of Alaska | Yes
Feb - March | UA Leadership | FY24 | Supplemental Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY25 | Amendment Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY25 | Budget Request - Legislative Status Report | BOR | Yes | Yes
Feb - March | Governor | FY25 | Amended budget scenario released | Legislature | Yes | Yes
March (early) | MAUs | FY24 | Lapsing Capital Appropriations Review/Extension Requests | SO SPB |  | CAT Process
April (early) | MAUs | FY24 | University Spring Management Report Review | UA Leadership | Yes | Yes
April - 15th | UA Leadership | AY25 | Tuition Rate Notice (letter from the President per BOR P05.10.060) | BOR
April | UA Leadership | FY24 | Budget Request - Legislative Status Report | BOR | Yes | Yes
April - June | SO SPB | FY24 | Lapsing Capital Appropriations Reviewed/Extended | DoF |  | CAT Process
April | SO SPB | FY25 | Operating and Capital Budget Distribution Plan Recommendation Developed | UA Leadership | OBD Process | CBD Process
April (late) | SO SPB | All | Capital Committed Funds & Transfer Reports Created | BOR |  | CAT Process
May | Legislature | FY25 | Leg: Budget submitted to Governor for signature and veto review Gov: Operating and capital bills are signed | Governor | Yes | Yes
May | SO DAIR | FY26 | Updated Draft Performance Management Evaluation Procedures Distributed | MAUs |  |  | PME Process |  | Designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
May | SO Finance | FY25 | Temporary budgets rolled in Banner | MAUs | Yes |  |  |  | Link to Finance year end calendar

## 2022
Fiscal Year | 22 | 23
UA Strategy, Planning and Budget Calendar Board of Regents Action/Reports and Other Significant Events all dates are subject to change as more/different guidance becomes available or specific dates will be provided when instructions are distributed
Date | Responsible Party | Year | Action/Event | Audience | Operating Budget | Capital Budget | Performance | Personal Services | Notes
May - August | MAUs* | FY24 | Initial MAU* performance reports created, including written analysis, definitions, baseline data | UA & MAU* Leadership |  |  | PME Process |  | *designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
June | President and senior leadership | FY23 | -Operating and Capital Budget Appropriation Acceptance -Operating and Capital Budget Distribution Plan Approval -Natural Resources Fund Budget Allocation Approval | BOR | OBD Process
June | SO SPB | FY24 | -Distribute instructions regarding: -Submitting Operating & Capital Budget Requests -Updating the 10-yr Capital Improvement Plan | MAUs | OBD Process | CBD Process
June | UA Leadership | FY24 | Budget, Goals, and Measures Planning Discussion | BOR | Yes |  | Yes
June - 20th | MAUs | FY23 | Initial budget entries due | SO SPB | Yes
June - 24th | SO SPB | FY23 | Initial budget entries to Finance | SO Finance | Yes
June - 24th | SO SPB | FY23 | Initial position budget entries to HR | SO HR | Yes
June 27th - July 1st | SO HR | FY23 | -No position data entry (NBAPOSN/NBAPBUD) after 5pm until notified by SO HR -HR Budgets Rolls to Zero through Budget activation | MAUs | Yes |  |  | Yes | Scroll to Fiscal Year Close Procedures
June - 30th | SO Finance | FY23 | Temporary unrestricted budgets reversed and permanent budgets loaded | MAUs | Yes |  |  |  | Scroll to Year End Instructions
July 1st |  | All | Fiscal year begins | UA | Yes |  | Yes | Yes
July | SO SPB | FY24 | Compensation and fixed cost budget estimates developed | MAUs | Yes |  |  | Yes
July | DoF | FY23 | New Capital Appropriation Collocation Codes Created/Distributed | SO SPB |  | CAT Process
July | SO SPB | FY23 | New Collocation Codes set up in Banner | MAUs |  | CAT Process
As Needed | MAUs | All | Funds Attached to Collocation Codes | SO SPB |  | CAT Process
July | SO SPB | FY24 | Instructions for completing ABS narrative sections issued | MAUs | Yes
July - 15th | MAUs | FY22 | Final Authorized: balance budget and Expenditures in Banner (allocation, object code, and fund source) prior to SO Finance roll | SO SPB | Yes
July - 16th | SO Finance | FY22 | Fiscal year roll in Banner | UA | Yes
July - 25th | MAUs | FY23 | Management Plan: balanced operating budget in Banner (allocation, object code, and fund source) | SO SPB | Yes
July - 31st | SO SPB | FY23 | Management Plan Budget (including personal services report) Scenario Due | OMB | Yes |  |  | Yes
August (early) | MAUs | FY24 | Submitted: Operating Budget Requests Capital Budget Requests 10-yr Capital Improvement Plan | SO SPB | OBD Process | CBD Process
August | MAUs | FY23 | Deferred Maintenance Expenditure Projections Submitted | SO SPB |  | CAT Process
August | SO SPB | FY24 | 10-yr Revenue Projections | OMB
August | MAUs | FY23 | Universities Budget Meeting | UA Leadership | Yes
August (mid) | MAUs | FY24 | Capital Budget Requests (DM/R&R) and Deferred Maintenance/Renewal & Repurposing Project list submitted | SO SPB |  | CBD Process
August | Chancellors | FY24 | Review and Provide input: Operating and Capital Budget Requests | President and senior leadership | OBD Process | CBD Process
August (end of month) | MAUs* | FY24 | Initial performance analyses published by MAUs* on OMB web site for public viewing, and used by UA Leadership in discussion during initial meetings with OMB. | OMB |  |  | PME Process |  | *designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September - November | MAUs* | FY24 | Final MAU* performance reports entered, including written analysis, definitions, baseline data, in alignment with the overall budget. Note: Content changes made later in this period typically undergo review, and may require OMB approval to publish. | UA Leadership |  |  | PME Process |  | *designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
September (early) | SO SPB | FY24 | Deferred Maintenance/Renewal & Repurposing Project list submitted | OMB |  | CBD Process
September | SO SPB | FY23 | Deferred Maintenance Expenditure Projections Submitted | OMB |  | CAT Process
September | UA Leadership | AY24 | Discussion and Approval of Tuition Rates | BOR | Yes
September | SO SPB | FY24 | Review: Operating Budget Request Capital Budget Request 10-yr Capital Improvement Plan | BOR | OBD Process | CBD Process
September | SO SPB | FY22 | Final Authorized and Actual Scenarios due in ABS | OMB | Yes
September | UA Leadership | FY24 | Initial Meetings with Legislative Finance Division | Leg. Fin. | OBD Process
September | UA Leadership | FY24 | Initial Meetings with OMB | OMB | OBD Process
September | SO SPB | FY23 | Capital Appropriation History Updated | UA |  | CAT Process
September (late) | SO SPB | FY23 | Authorized Budget Distribution Document (Yellowbook) Published | UA
October | MAUs | FY24 | Complete MAU Level Operating Budget Narratives & Org Charts for ABS | SO SPB | Yes
October | SO SPB | All | Capital Committed Funds & Transfer Reports Created | BOR |  | CAT Process
October (late) | SO SPB | FY24 | UA Level Narrative Submitted | OMB | Yes
November (early) | UA Leadership | FY24 | Approval: Operating Budget Request Capital Budget Request 10-yr Capital Improvement Plan | BOR | OBD Process | CBD Process
November (early) | SO Finance | FY22 | Financial Statements Audited Financial Statements Available | BOR
November | SO SPB | FY24 | MAU Level Operating Budget Narratives & Org Charts in ABS | OMB | Yes
November | SO SPB | FY24 | Submitted: Operating Budget Capital Budget | OMB | OBD Process | CBD Process
November (end of month) | MAUs* | FY24 | Final MAU* performance analysis published via OMB action on website for public viewing and locked until next cycle. | OMB |  |  | PME Process |  | *Hard stop due date set by SO SPB, as select content is included in both UA Budget book and Governor's Budget Proposal. In recent years, this has occurred in early December.
December | SO SPB | FY24 | Due: Gov/UA Budget Book due NOTE: Once this is submitted, OMB will not allow changes to published performance analysis content until the next reporting cycle. | OMB | Yes | Yes | Yes | Yes
December 15th | Governor | FY24 | Budget Proposal submitted to Legislature | Legislature | Yes | Yes
December (late) | MAUs | FY23 | Due: Capital Appropriation Status Updates (CASR) | SO SPB |  | CBD Process
January (early) | SO SPB | FY23 | Due: Capital Appropriations Status Reports (CASR) | OMB |  | CBD Process
January (early) | SO SPB | FY23 | Submit supplemental request(s) to OMB | OMB | Yes | Yes
January (early) | SO SPB | FY24 | Discuss possible budget amendments with OMB | OMB | Yes | Yes
January | SO SPB | FY24 | Operating and Capital Budget Document Published (aka Redbook) | UA | OBD Process | CBD Process | Yes
January | Legislature | All | Legislative Session Begins 3rd Tuesday in January | State of Alaska | Yes
Feb - March | UA Leadership | FY23 | Supplemental Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY24 | Amendment Request Approval (if applicable) | BOR | Yes | Yes
Feb - March | UA Leadership | FY24 | Budget Request - Legislative Status Report | BOR | Yes | Yes
Feb - March | Governor | FY24 | Amended budget scenario released | Legislature | Yes | Yes
March (early) | MAUs | FY23 | Lapsing Capital Appropriations Review/Extension Requests | SO SPB |  | CAT Process
April (early) | MAUs | FY23 | University Spring Management Report Review | UA Leadership | Yes | Yes
April - 15th | UA Leadership | AY24 | Tuition Rate Notice (letter from the President per BOR P05.10.060) | BOR
April | UA Leadership | FY23 | Budget Request - Legislative Status Report | BOR | Yes | Yes
April - June | SO SPB | FY23 | Lapsing Capital Appropriations Reviewed/Extended | DoF |  | CAT Process
April | SO SPB | FY24 | Operating and Capital Budget Distribution Plan Recommendation Developed | UA Leadership | OBD Process | CBD Process
April (late) | SO SPB | All | Capital Committed Funds & Transfer Reports Created | BOR |  | CAT Process
May | Legislature | FY24 | Leg: Budget submitted to Governor for signature and veto review Gov: Operating and capital bills are signed | Governor | Yes | Yes
May | SO DAIR | FY25 | Updated Draft Performance Management Evaluation Procedures Distributed | MAUs* |  |  | PME Process |  | *designated coordinating point person assigned for UAA, UAF, UAS, SO, EE & UA reports
May | SO Finance | FY24 | Temporary budgets rolled in Banner | MAUs | Yes |  |  |  | Link to Finance year end calendar

## 2021
Fiscal Year | 21 | 22 |  | Finance Dates | HR Dates | OMB | SBP | PME Date | Source department for dates
UA Strategy, Planning and Budget Calendar Board of Regents Action/Reports and Other Significant Events all dates are subject to change as more/different guidance becomes available or specific dates will be provided when instructions are distributed
Date | Responsible Party | Year | Action/Event | Audience | Operating Budget | Capital Budget | Performance | Personal Services | Notes
June | President and senior leadership | FY22 | Operating and Capital Budget Appropriation Acceptance Operating and Capital Budget Distribution Plan Approval Natural Resources Fund Budget Allocation Approval | BOR | OBD Process
June | SO SPB | FY23 | Distribute instructions regarding: Submitting Operating & Capital Budget Requests Updating the 10-yr Capital Improvement Plan | MAUs | OBD Process | CBD Process
June | UA Leadership | FY23 | Budget, Goals, and Measures Planning Discussion | BOR | Yes |  | Yes
June - 21st | MAUs | FY22 | Initial budget entries due | SO SPB | Yes
June - July | MAUs | FY23 | Working metrics and reporting definitions identified and updated/created, including definitions, baseline data and analysis | UA Leadership |  |  | PME Process
June - 25th | SO SPB | FY22 | Initial budget entries to Finance | SO Finance | Yes
June - 25th | SO SPB | FY22 | Initial position budget entries to HR | SO HR | Yes
June 28th - July 2nd | SO HR | FY22 | No position data entry (NBAPOSN/NBAPBUD) after 5pm until notified by SO HR HR Budgets Rolls to Zero through Budget activation | MAUs | Yes |  |  | Yes | Link to HR year end calendar
June - 30th | SO Finance | FY22 | Temporary unrestricted budgets reversed and permanent budgets loaded | MAUs | Yes
July 1st |  | All | Fiscal year begins | UA | Yes |  | Yes | Yes
July | SO SPB | FY23 | Compensation and fixed cost budget estimates developed | MAUs | Yes |  |  | Yes
July | DoF | FY22 | New Capital Appropriation Collocation Codes Created/Distributed | SO SPB |  | CAT Process
July | SO SPB | FY22 | New Collocation Codes set up in Banner | MAUs |  | CAT Process
As Needed | MAUs | All | Funds Attached to Collocation Codes | SO SPB |  | CAT Process
July | SO SPB | FY23 | Instructions for completing ABS narrative sections issued | MAUs | Yes
July - 16th | MAUs | FY21 | Balance Budget and Expenditures in Banner (allocation, object code, and fund source) prior to SO Finance roll | SO SPB | Yes
July - 17th | SO Finance | FY21 | Fiscal year roll in Banner | UA | Yes
July - 26th | MAUs | FY22 | Balanced operating budget in Banner (allocation, object code, and fund source) | SO SPB | Yes
July - 31st | SO SPB | FY22 | Management Plan Budget (including personal services report) Scenario Due | OMB | Yes |  |  | Yes
August (early) | MAUs | FY23 | Submitted: Operating Budget Requests Capital Budget Requests 10-yr Capital Improvement Plan | SO SPB | OBD Process | CBD Process
August 2nd | MAUs | FY23 | Submission Deadline: Preliminary performance report analysis via OMB web site for initial review and comment | SO IR, SPB |  |  | PME Process
August | MAUs | FY22 | Deferred Maintenance Expenditure Projections Submitted | SO SPB |  | CAT Process
August 9th | SO IR | FY23 | Submission Deadline: Detailed questions, comments, technical items to resolve on preliminary performance reports | MAUs |  |  | PME Process
August | SO SPB | FY2022 | 10-yr Revenue Projections | OMB
August | MAUs | FY22 | Universities Budget Meeting | UA Leadership | Yes
August | MAUs | FY23 | Capital Budget Requests (DM/R&R) and Deferred Maintenance/Renewal & Repurposing Project list submitted | SO SPB
August 23rd | MAUs | FY23 | Final draft performance analysis report reflecting feedback from first draft | SO IR, SPB |  |  | PME Process
August 24th | SO IR | FY23 | Summary and detail of performance analyses circulated for leadership awareness and talking points | UA Leadership |  |  | PME Process
August | Chancellors and system-wide councils | FY23 | Review and Provide input: Operating and Capital Budget Requests | President and senior leadership | OBD Process | CBD Process
September - 1st | SO IR | FY23 | Performance analyses published on OMB web site and used in discussion during initial meetings with OMB. Note: Changes after this date need to be approved by UA, then OMB staff. | OMB |  |  | PME Process
September (early) | SO SPB | FY23 | Deferred Maintenance/Renewal & Repurposing Project list submitted | OMB
September | SO SPB | FY22 | Deferred Maintenance Expenditure Projections Submitted | OMB |  | CAT Process
September | UA Leadership | AY23 | Discussion and Approval of Tuition Rates | BOR | Yes
September | SO SPB | FY23 | Review: Operating Budget Request Capital Budget Request 10-yr Capital Improvement Plan | BOR | OBD Process | CBD Process
September | SO SPB | FY21 | Final Authorized and Actual Scenarios due in ABS | OMB | Yes
September | MAUs | FY23 | Complete operating budget narratives for ABS | SO SPB | Yes
September | UA Leadership | FY23 | Initial Meetings with Legislative Finance Division | Leg. Fin. | OBD Process
September | UA Leadership | FY23 | Initial Meetings with OMB | OMB | OBD Process
September | SO SPB | FY22 | Capital Appropriation History Updated | UA
September (late) | SO SPB | FY22 | Authorized Budget Distribution Document (Yellowbook) Published | UA
October | SO SPB | All | Committed Funds & Transfer Reports Created | BOR
November (early) | UA Leadership | FY23 | Approval: Operating Budget Request Capital Budget Request 10-yr Capital Improvement Plan | BOR | OBD Process | CBD Process
November (early) | SO Finance | FY21 | Financial Statements Audited Financial Statements Available | BOR | Yes
November | SO SPB | FY23 | Submitted: Operating Budget Capital Budget | OMB | OBD Process | CBD Process
November | OMB | FY23 | Performance information locked for release of Governor's budget. |  |  |  | PME Process |  | Last submission date: 11/17/2019
December | SO SPB | FY23 | UA Budget Book due NOTE: Once this is submitted, OMB will not allow changes to published performance analysis content until the next reporting cycle. | OMB | Yes |  | Yes | Yes
December 15th | Governor | FY23 | Budget Proposal submitted to Legislature | Legislature | Yes
December (late) | MAUs | FY22 | Capital Appropriation Status Updates Due | SO SPB
January (early) | SO SPB | FY22 | Capital Appropriations Status Reports (CASR) Due | OMB
January (early) | SO SPB | FY22 | Submit supplemental request(s) to OMB | OMB | Yes
January (early) | SO SPB | FY23 | Discuss possible budget amendments with OMB | OMB | Yes
January | SO SPB | FY23 | Operating and Capital Budget Document Published (aka Redbook) | UA | OBD Process | CBD Process | Yes
January | Legislature | All | Legislative Session Begins 3rd Tuesday in January | State of Alaska | Yes
Feb - March | UA Leadership | FY22 | Supplemental Request Approval (if applicable) | BOR | Yes
Feb - March | UA Leadership | FY23 | Amendment Request Approval (if applicable) | BOR | Yes
Feb - March | UA Leadership | FY23 | Budget Request - Legislative Status Report | BOR | Yes
Feb - March | Governor | FY23 | Amended budget scenario released | Legislature | Yes
March (early) | MAUs | FY22 | Lapsing Capital Appropriations Review/Extension Requests | SO SPB |  | CAT Process
April (early) | MAUs | FY22 | University Spring Management Report Review | UA Leadership | Yes | Yes
April | UA Leadership | AY23 | Tuition Rate Notice (letter from the President per BOR P05.10.060) | BOR | Yes
April | UA Leadership | FY22 | Budget Request - Legislative Status Report | BOR | Yes | Yes
April - June | SO SPB | FY22 | Lapsing Capital Appropriations Reviewed/Extended | DoF |  | CAT Process
April | SO SPB | FY23 | Operating and Capital Budget Distribution Plan Recommendation Developed | UA Leadership | OBD Process | CBD Process
April (late) | SO SPB | All | Committed Funds & Transfer Reports Created | BOR |  | CAT Process
May | Legislature | FY23 | Leg: Budget submitted to Governor for signature and veto review Gov: Operating and capital bills are signed | Governor | Yes | Yes
May | SO IR | FY24 | Updated Draft Performance Management Evaluation Procedures Distributed | MAUs |  |  | PME Process
May | SO Finance | FY23 | Temporary budgets rolled in Banner | MAUs | Yes |  |  |  | Link to Finance year end calendar